## Sheet3
ID | Date | Project | Title
1 | 2019-03-03 | MEDORE_CR18_JLT | Fwd message
2 | 2019-03-03 | MEDORE_CR18_JLT | Well received
3 | 2019-03-04 | MEDORE_CR18_JLT | Create folder
4 | 2019-03-04 | MEDORE_CR18_JLT | Done
5 | 2019-03-05 | MEDORE_CR18_JLT | Quotation to Adel (CRC)
6 | 2019-03-07 | MEDORE_CR18_JLT | Enquiry for Steel
7 | 2019-03-10 | MEDORE_CR18_JLT | Reminder
8 | 2019-03-12 | MEDORE_CR18_JLT | Per Sqm Steel Quotation
9 | 2019-03-14 | MEDORE_CR18_JLT | Revised Quotation CRC
10 | 2019-05-15 | MEDORE_CR18_JLT | Dutco Enquiry
11 | 2019-05-16 | MEDORE_CR18_JLT | Quotation to Dutco
12 | 2019-06-02 | MEDORE_CR18_JLT | Revised Quotation CRC
13 | 2019-08-25 | MEDORE_CR18_JLT | Dutco Enquiry
14 | 2019-08-25 | MEDORE_CR18_JLT | Quotation Ayman (Dutco)
15 | 2019-08-26 | MEDORE_CR18_JLT | Fwd Email
16 | 2019-09-05 | MEDORE_CR18_JLT | Dutco Clarification
17 | 2019-09-09 | MEDORE_CR18_JLT | Need revised Quote
18 | 2019-09-10 | MEDORE_CR18_JLT | Still waiting (Dutco)
19 | 2019-09-11 | MEDORE_CR18_JLT | Soft reminder steel
20 | 2019-09-11 | MEDORE_CR18_JLT | Updated Offer
21 | 2019-09-16 | MEDORE_CR18_JLT | Site visit required
22 | 2019-09-17 | MEDORE_CR18_JLT | Can arrange tomorrow
23 | 2019-09-18 | MEDORE_CR18_JLT | Revised Quote
24 | 2019-09-19 | MEDORE_CR18_JLT | Mail sameh
25 | 2019-09-24 | MEDORE_CR18_JLT | Updated offer
26 | 2019-09-29 | MEDORE_CR18_JLT | Section details MEDORE
27 | 2019-10-06 | MEDORE_CR18_JLT | PT Works mercedez
28 | 2019-10-10 | MEDORE_CR18_JLT | Reminder 1
29 | 2019-10-13 | MEDORE_CR18_JLT | Details to Bitar
30 | 2019-10-13 | MEDORE_CR18_JLT | Link
31 | 2019-10-13 | MEDORE_CR18_JLT | Soft reminder # 2
32 | 2019-10-14 | MEDORE_CR18_JLT | NDA
33 | 2019-10-14 | MEDORE_CR18_JLT | Signed NDA
34 | 2019-10-14 | MEDORE_CR18_JLT | Etabs model
35 | 2019-10-16 | MEDORE_CR18_JLT | Revised Steel quote
36 | 2019-10-16 | MEDORE_CR18_JLT | Revised quote
37 | 2019-10-16 | MEDORE_CR18_JLT | Error in model
38 | 2019-10-16 | MEDORE_CR18_JLT | Typo modified
39 | 2019-10-16 | MEDORE_CR18_JLT | Link for model
40 | 2019-10-16 | MEDORE_CR18_JLT | Again errors
41 | 2019-10-17 | MEDORE_CR18_JLT | Quotation required
42 | 2019-10-17 | MEDORE_CR18_JLT | Quotation required
43 | 2019-10-17 | MEDORE_CR18_JLT | Not our scope
44 | 2019-10-17 | MEDORE_CR18_JLT | Details to Feroz
45 | 2019-10-17 | MEDORE_CR18_JLT | Thanks for enquiry
46 | 2019-10-20 | MEDORE_CR18_JLT | Link to Omar ETABS
47 | 2019-10-20 | MEDORE_CR18_JLT | Revised Steel offer
48 | 2019-10-20 | MEDORE_CR18_JLT | Propping by others
49 | 2019-10-20 | MEDORE_CR18_JLT | Thanks for offer
50 | 2019-10-20 | MEDORE_CR18_JLT | Lets meet tomorrow USW
51 | 2019-10-20 | MEDORE_CR18_JLT | Confirmed
52 | 2019-10-20 | MEDORE_CR18_JLT | ETABS to bitar
53 | 2019-10-21 | MEDORE_CR18_JLT | Revised quote pooja
54 | 2019-10-21 | MEDORE_CR18_JLT | Details to Feroz
55 | 2019-10-21 | MEDORE_CR18_JLT | Carried design checks
56 | 2019-10-22 | MEDORE_CR18_JLT | Revised offer steel
57 | 2019-10-22 | MEDORE_CR18_JLT | Updated offer Tamer (Client)
58 | 2019-11-03 | MEDORE_CR18_JLT | Quotation followup
59 | 2019-11-12 | MEDORE_CR18_JLT | Reminder
60 | 2019-12-11 | MEDORE_CR18_JLT | China railway PT enquiry
61 | 2019-12-12 | MEDORE_CR18_JLT | PT revised enquiry
62 | 2019-12-12 | MEDORE_CR18_JLT | Pooja to sameh
63 | 2019-12-12 | MEDORE_CR18_JLT | Quotation to Liza Combined
64 | 2019-12-12 | MEDORE_CR18_JLT | Reminder steel
65 | 2019-12-12 | MEDORE_CR18_JLT | Response to Technosteel
66 | 2019-12-17 | MEDORE_CR18_JLT | Meeting tomorrow
67 | 2019-12-17 | MEDORE_CR18_JLT | Confirmed to Nithin
68 | 2019-12-19 | MEDORE_CR18_JLT | Revised column layout
69 | 2019-12-22 | MEDORE_CR18_JLT | Submit prequalification
70 | 2019-12-22 | MEDORE_CR18_JLT | Attend meeting
71 | 2019-12-22 | MEDORE_CR18_JLT | Confirmed attendance
72 | 2019-12-22 | MEDORE_CR18_JLT | Prequalification to King
73 | 2019-12-22 | MEDORE_CR18_JLT | Quotations to Nithin
74 | 2019-12-23 | MEDORE_CR18_JLT | Send revised quote Feroz
75 | 2019-12-23 | MEDORE_CR18_JLT | Send revised quote Techno
76 | 2019-12-23 | MEDORE_CR18_JLT | Structural drawings Bitar
77 | 2019-12-23 | MEDORE_CR18_JLT | Mail for nithin
78 | 2019-12-23 | MEDORE_CR18_JLT | Revised mail
79 | 2019-12-23 | MEDORE_CR18_JLT | Email Jiang
80 | 2019-12-24 | MEDORE_CR18_JLT | Revised United Steel
81 | 2019-12-24 | MEDORE_CR18_JLT | Revised Technosteel
82 | 2019-12-25 | MEDORE_CR18_JLT | Meeting with client
83 | 2019-12-25 | MEDORE_CR18_JLT | Noted
84 | 2019-12-25 | MEDORE_CR18_JLT | PT Drawings Link
85 | 2019-12-25 | MEDORE_CR18_JLT | PT quotation
86 | 2019-12-25 | MEDORE_CR18_JLT | Link for drawings
87 | 2019-12-26 | MEDORE_CR18_JLT | Drawings to Mohammad
88 | 2019-12-26 | MEDORE_CR18_JLT | Link for full drawings
89 | 2019-12-26 | MEDORE_CR18_JLT | Submit prequalification
90 | 2019-12-26 | MEDORE_CR18_JLT | Final quotations to Jiang
91 | 2019-12-26 | MEDORE_CR18_JLT | Prequalification submitted
92 | 2019-12-26 | MEDORE_CR18_JLT | Reply to Feroz (USW)
93 | 2019-12-26 | MEDORE_CR18_JLT | Enquiry MEDI Steel
94 | 2019-12-26 | MEDORE_CR18_JLT | Well received
95 | 2019-12-28 | MEDORE_CR18_JLT | Layout 3rd floor
96 | 2019-12-28 | MEDORE_CR18_JLT | Thanks
97 | 2019-12-28 | MEDORE_CR18_JLT | Revised USW Steel Qtn
98 | 2019-12-28 | MEDORE_CR18_JLT | PT Agreement
99 | 2019-12-29 | MEDORE_CR18_JLT | Reply as comments
100 | 2019-12-29 | MEDORE_CR18_JLT | Offer Steel works MEDI
101 | 2019-12-29 | MEDORE_CR18_JLT | Thankful for offer
102 | 2019-12-29 | MEDORE_CR18_JLT | Approvals and CVs to be submitted
103 | 2019-12-29 | MEDORE_CR18_JLT | Atef CV
104 | 2019-12-29 | MEDORE_CR18_JLT | Strengthening Agreement
105 | 2019-12-29 | MEDORE_CR18_JLT | Atef Nageh Mohammed CV
106 | 2019-12-29 | MEDORE_CR18_JLT | Comments strengthening agreement
107 | 2019-12-29 | MEDORE_CR18_JLT | Omar give CV
108 | 2019-12-29 | MEDORE_CR18_JLT | Also Odai
109 | 2019-12-30 | MEDORE_CR18_JLT | Suleiman CV
110 | 2019-12-30 | MEDORE_CR18_JLT | Reminder
111 | 2019-12-30 | MEDORE_CR18_JLT | Sameh CV
112 | 2019-12-30 | MEDORE_CR18_JLT | Omar CV
113 | 2019-12-30 | MEDORE_CR18_JLT | Odai CV
114 | 2019-12-30 | MEDORE_CR18_JLT | Al-Torath Documents
115 | 2019-12-30 | MEDORE_CR18_JLT | Documents to China Railway
116 | 2019-12-30 | MEDORE_CR18_JLT | Drawings and BOQ Atef
117 | 2019-12-31 | MEDORE_CR18_JLT | Details to Eversendai (Steel works)
118 | 2020-01-02 | MEDORE_CR18_JLT | Update on contract agreement
119 | 2020-01-02 | MEDORE_CR18_JLT | Gunite machines comparison
120 | 2020-01-02 | MEDORE_CR18_JLT | Final revised subcontract agreement
121 | 2020-01-02 | MEDORE_CR18_JLT | Fwd to Bitar
122 | 2020-01-02 | MEDORE_CR18_JLT | Thankful and arrange meeting
123 | 2020-01-02 | MEDORE_CR18_JLT | Meeting time and location
124 | 2020-01-04 | MEDORE_CR18_JLT | Eversendai queries
125 | 2020-01-04 | MEDORE_CR18_JLT | Structural drawings AutoCAD
126 | 2020-01-04 | MEDORE_CR18_JLT | Make A1 print
127 | 2020-01-04 | MEDORE_CR18_JLT | Arrange introductory meeting
128 | 2020-01-04 | MEDORE_CR18_JLT | DESCO for print
129 | 2020-01-04 | MEDORE_CR18_JLT | Meeting details
130 | 2020-01-04 | MEDORE_CR18_JLT | Confirmed
131 | 2020-01-04 | MEDORE_CR18_JLT | Link to Bitar
132 | 2020-01-04 | MEDORE_CR18_JLT | ReCon SM technical submittal
133 | 2020-01-04 | MEDORE_CR18_JLT | Response to Eversendai
134 | 2020-01-04 | MEDORE_CR18_JLT | Will check
135 | 2020-01-05 | MEDORE_CR18_JLT | Site visit required
136 | 2020-01-05 | MEDORE_CR18_JLT | Atef to coordinate
137 | 2020-01-05 | MEDORE_CR18_JLT | Details to Ali Ansary
138 | 2020-01-05 | MEDORE_CR18_JLT | Sika dry shotcrete
139 | 2020-01-05 | MEDORE_CR18_JLT | Make BBS
140 | 2020-01-05 | MEDORE_CR18_JLT | Final draft agreement
141 | 2020-01-06 | MEDORE_CR18_JLT | Manpower agreement
142 | 2020-01-06 | MEDORE_CR18_JLT | BRC prequalification
143 | 2020-01-06 | MEDORE_CR18_JLT | Handed over 2 sets
144 | 2020-01-06 | MEDORE_CR18_JLT | FYI BRC
145 | 2020-01-06 | MEDORE_CR18_JLT | DM Stamped Drawings & Forms
146 | 2020-01-07 | MEDORE_CR18_JLT | About meeting Conmix
147 | 2020-01-07 | MEDORE_CR18_JLT | Submittals to be arranged
148 | 2020-01-07 | MEDORE_CR18_JLT | A2 print
149 | 2020-01-07 | MEDORE_CR18_JLT | Latest ETABS models
150 | 2020-01-07 | MEDORE_CR18_JLT | RFI form
151 | 2020-01-07 | MEDORE_CR18_JLT | Fwd FYI
152 | 2020-01-07 | MEDORE_CR18_JLT | Re-schedule Saturday
153 | 2020-01-07 | MEDORE_CR18_JLT | Ali Ansaries Email
154 | 2020-01-07 | MEDORE_CR18_JLT | Send equipment requirements
155 | 2020-01-08 | MEDORE_CR18_JLT | Manpower quotation
156 | 2020-01-08 | MEDORE_CR18_JLT | PT meeting
157 | 2020-01-08 | MEDORE_CR18_JLT | Wet shotcrete
158 | 2020-01-08 | MEDORE_CR18_JLT | Confirm meeting attendance
159 | 2020-01-08 | MEDORE_CR18_JLT | Technosteel followup
160 | 2020-01-08 | MEDORE_CR18_JLT | Monday meeting Conmix
161 | 2020-01-08 | MEDORE_CR18_JLT | Repair tools in store
162 | 2020-01-08 | MEDORE_CR18_JLT | Workshop meeting technosteel
163 | 2020-01-08 | MEDORE_CR18_JLT | Need repair tools
164 | 2020-01-09 | MEDORE_CR18_JLT | TS location map
165 | 2020-01-09 | MEDORE_CR18_JLT | ACE account opening
166 | 2020-01-09 | MEDORE_CR18_JLT | Section details TS
167 | 2020-01-09 | MEDORE_CR18_JLT | Compressor datasheet
168 | 2020-01-09 | MEDORE_CR18_JLT | Yes its fine
169 | 2020-01-09 | MEDORE_CR18_JLT | Hiring compressor Quotation
170 | 2020-01-11 | MEDORE_CR18_JLT | Certificates
171 | 2020-01-11 | MEDORE_CR18_JLT | Mix-design details required
172 | 2020-01-11 | MEDORE_CR18_JLT | Final BOQ
173 | 2020-01-11 | MEDORE_CR18_JLT | Prequalification submitted
174 | 2020-01-12 | MEDORE_CR18_JLT | Cutting only BOQ
175 | 2020-01-12 | MEDORE_CR18_JLT | Look-ahead program
176 | 2020-01-12 | MEDORE_CR18_JLT | Inquiry for labor supply
177 | 2020-01-12 | MEDORE_CR18_JLT | Soft reminder TS
178 | 2020-01-12 | MEDORE_CR18_JLT | Manpower quotation
179 | 2020-01-12 | MEDORE_CR18_JLT | Send power requirements
180 | 2020-01-12 | MEDORE_CR18_JLT | Tools to be used
181 | 2020-01-12 | MEDORE_CR18_JLT | KW-KVA required
182 | 2020-01-12 | MEDORE_CR18_JLT | Murugesan meeting
183 | 2020-01-12 | MEDORE_CR18_JLT | Ali bhai meeting
184 | 2020-01-12 | MEDORE_CR18_JLT | Slab areas bitar
185 | 2020-01-12 | MEDORE_CR18_JLT | Ali confirmed
186 | 2020-01-12 | MEDORE_CR18_JLT | Murugesan Confirmed
187 | 2020-01-12 | MEDORE_CR18_JLT | Whats value
188 | 2020-01-12 | MEDORE_CR18_JLT | Final BOQ bitar
189 | 2020-01-13 | MEDORE_CR18_JLT | Technosteel final quotation
190 | 2020-01-13 | MEDORE_CR18_JLT | Manpower Qtn discount req
191 | 2020-01-13 | MEDORE_CR18_JLT | Manpower Qtn discount req
192 | 2020-01-13 | MEDORE_CR18_JLT | 5% discount possible
193 | 2020-01-13 | MEDORE_CR18_JLT | Sika & Conmix datasheets
194 | 2020-01-13 | MEDORE_CR18_JLT | Recon & LVE submittal
195 | 2020-01-13 | MEDORE_CR18_JLT | Nanogrout CFG
196 | 2020-01-14 | MEDORE_CR18_JLT | Enquiry for ali
197 | 2020-01-14 | MEDORE_CR18_JLT | Shotcrete test results
198 | 2020-01-14 | MEDORE_CR18_JLT | Conmix submittal MC80
199 | 2020-01-14 | MEDORE_CR18_JLT | Fwd armia atef
200 | 2020-01-14 | MEDORE_CR18_JLT | Have meeting
201 | 2020-01-15 | MEDORE_CR18_JLT | Enquiry to Ali
202 | 2020-01-15 | MEDORE_CR18_JLT | Submit material submittal
203 | 2020-01-15 | MEDORE_CR18_JLT | Thickness of anchors
204 | 2020-01-15 | MEDORE_CR18_JLT | Reply to Ali
205 | 2020-01-15 | MEDORE_CR18_JLT | Enquiry AlManara
206 | 2020-01-15 | MEDORE_CR18_JLT | Hilti Tool Pricing
207 | 2020-01-15 | MEDORE_CR18_JLT | Complete submittal
208 | 2020-01-15 | MEDORE_CR18_JLT | Will send tomorrow
209 | 2020-01-15 | MEDORE_CR18_JLT | 3 sets required
210 | 2020-01-15 | MEDORE_CR18_JLT | Make 3 books
211 | 2020-01-16 | MEDORE_CR18_JLT | Make 2 CDs
212 | 2020-01-18 | MEDORE_CR18_JLT | Manara Quotation
213 | 2020-01-18 | MEDORE_CR18_JLT | Fwd armia atef
214 | 2020-01-18 | MEDORE_CR18_JLT | Enquiry Khouram
215 | 2020-01-19 | MEDORE_CR18_JLT | Revised Manara Qtn
216 | 2020-01-20 | MEDORE_CR18_JLT | Shutter materials CCL Store
217 | 2020-01-20 | MEDORE_CR18_JLT | Enquiry RMD Shuttering
218 | 2020-01-20 | MEDORE_CR18_JLT | Ali bhai reminder
219 | 2020-01-20 | MEDORE_CR18_JLT | Martin Sika materials
220 | 2020-01-20 | MEDORE_CR18_JLT | Fwd sika materials
221 | 2020-01-20 | MEDORE_CR18_JLT | Shuttering details Nageh
222 | 2020-01-20 | MEDORE_CR18_JLT | Estimation follow-up
223 | 2020-01-20 | MEDORE_CR18_JLT | Ali bhai Quotation
224 | 2020-01-21 | MEDORE_CR18_JLT | BOQ print
225 | 2020-01-21 | MEDORE_CR18_JLT | Cutting Qtn 1
226 | 2020-01-21 | MEDORE_CR18_JLT | Cutting Qtn 2
227 | 2020-01-21 | MEDORE_CR18_JLT | Nageh shuttering CCL store
228 | 2020-01-21 | MEDORE_CR18_JLT | Comments to Ali bhai
229 | 2020-01-21 | MEDORE_CR18_JLT | Atef reply Technosteel
230 | 2020-01-21 | MEDORE_CR18_JLT | Pricing request Sika
231 | 2020-01-21 | MEDORE_CR18_JLT | submittal prepared sika
232 | 2020-01-21 | MEDORE_CR18_JLT | Revised Qtn Ali Ansary
233 | 2020-01-22 | MEDORE_CR18_JLT | Cutting works Qtn + pics
234 | 2020-01-22 | MEDORE_CR18_JLT | Shuttering enquiry stengulf
235 | 2020-01-22 | MEDORE_CR18_JLT | Initial program
236 | 2020-01-22 | MEDORE_CR18_JLT | Pricing request Conmix
237 | 2020-01-22 | MEDORE_CR18_JLT | Draft contract Charminar
238 | 2020-01-22 | MEDORE_CR18_JLT | Tentative Qty
239 | 2020-01-22 | MEDORE_CR18_JLT | Sent
240 | 2020-01-22 | MEDORE_CR18_JLT | Charminar Agreement
241 | 2020-01-22 | MEDORE_CR18_JLT | Agreement Hind
242 | 2020-01-22 | MEDORE_CR18_JLT | Kurt pls print books
243 | 2020-01-22 | MEDORE_CR18_JLT | Email well received
244 | 2020-01-22 | MEDORE_CR18_JLT | Consultant response on RFI1&2 - IMP
245 | 2020-01-22 | MEDORE_CR18_JLT | Pls copy Omar
246 | 2020-01-23 | MEDORE_CR18_JLT | Hilti Quotation
247 | 2020-01-23 | MEDORE_CR18_JLT | Revised enquiry USW
248 | 2020-01-23 | MEDORE_CR18_JLT | Scaffolding enquiry Musandam
249 | 2020-01-23 | MEDORE_CR18_JLT | Eversendai revised steel
250 | 2020-01-23 | MEDORE_CR18_JLT | Provide as-built (by Omar) - IMP
251 | 2020-01-23 | MEDORE_CR18_JLT | Typo
252 | 2020-01-23 | MEDORE_CR18_JLT | Ooma subcontract
253 | 2020-01-23 | MEDORE_CR18_JLT | Sika Pricing
254 | 2020-01-23 | MEDORE_CR18_JLT | FYI sika prices
255 | 2020-01-23 | MEDORE_CR18_JLT | Musandam proposal
256 | 2020-01-23 | MEDORE_CR18_JLT | PT approved drawings - IMP
257 | 2020-01-23 | MEDORE_CR18_JLT | Conmix Pricing
258 | 2020-01-23 | MEDORE_CR18_JLT | Bitar to riyaz
259 | 2020-01-24 | MEDORE_CR18_JLT | Riyaz reply
260 | 2020-01-24 | MEDORE_CR18_JLT | Noted
261 | 2020-01-25 | MEDORE_CR18_JLT | Manoj query Eversendai
262 | 2020-01-25 | MEDORE_CR18_JLT | Omar reply Riyaz
263 | 2020-01-25 | MEDORE_CR18_JLT | USW Revised Steel Qtn
264 | 2020-01-25 | MEDORE_CR18_JLT | Stengulf Qtn - Fadi
265 | 2020-01-26 | MEDORE_CR18_JLT | Conmix prices FYI
266 | 2020-01-26 | MEDORE_CR18_JLT | Scaffolding enquiry
267 | 2020-01-26 | MEDORE_CR18_JLT | Sent to Mr. Nabil
268 | 2020-01-26 | MEDORE_CR18_JLT | Anchofix from Bitar
269 | 2020-01-26 | MEDORE_CR18_JLT | Draft casting plan
270 | 2020-01-26 | MEDORE_CR18_JLT | Email to Hilti for RE-100
271 | 2020-01-26 | MEDORE_CR18_JLT | Accessories update Stengulf
272 | 2020-01-27 | MEDORE_CR18_JLT | AutoCAD Dwgs required - IMP
273 | 2020-01-27 | MEDORE_CR18_JLT | Commented MS-Cracks & Raft
274 | 2020-01-27 | MEDORE_CR18_JLT | Commented Mat-Cracks & Raft
275 | 2020-01-27 | MEDORE_CR18_JLT | Crack markup- project team
276 | 2020-01-27 | MEDORE_CR18_JLT | Sika submittal req
277 | 2020-01-27 | MEDORE_CR18_JLT | Will receive
278 | 2020-01-27 | MEDORE_CR18_JLT | RMD working
279 | 2020-01-27 | MEDORE_CR18_JLT | Project name
280 | 2020-01-27 | MEDORE_CR18_JLT | Best pricing Fosroc req
281 | 2020-01-27 | MEDORE_CR18_JLT | Proposed casting plan comments
282 | 2020-01-27 | MEDORE_CR18_JLT | RMD Quotation
283 | 2020-01-27 | MEDORE_CR18_JLT | Sika Quotation Injection
284 | 2020-01-27 | MEDORE_CR18_JLT | Sikacrete 113PP price req
285 | 2020-01-27 | MEDORE_CR18_JLT | Archive it (Wall related)
286 | 2020-01-27 | MEDORE_CR18_JLT | Look ahead and delays
287 | 2020-01-27 | MEDORE_CR18_JLT | PG200 approvals - Conmix
288 | 2020-01-27 | MEDORE_CR18_JLT | ReCON MC5 submittal
289 | 2020-01-27 | MEDORE_CR18_JLT | ReCON MC5 submittal
290 | 2020-01-27 | MEDORE_CR18_JLT | StenGulf quotation
291 | 2020-01-27 | MEDORE_CR18_JLT | Fosroc submittal info email
292 | 2020-01-27 | MEDORE_CR18_JLT | Nitofill EPLV
293 | 2020-01-27 | MEDORE_CR18_JLT | Nitofill UR63
294 | 2020-01-27 | MEDORE_CR18_JLT | Nitofill WS60
295 | 2020-01-27 | MEDORE_CR18_JLT | Nitomortar FCB
296 | 2020-01-27 | MEDORE_CR18_JLT | Nitomortar FC
297 | 2020-01-27 | MEDORE_CR18_JLT | Musandam Credit application
298 | 2020-01-27 | MEDORE_CR18_JLT | Bitar response to Delay issue
299 | 2020-01-27 | MEDORE_CR18_JLT | Update scaffolding Qtn
300 | 2020-01-27 | MEDORE_CR18_JLT | Sarath response
301 | 2020-01-27 | MEDORE_CR18_JLT | Fosroc submittal req
302 | 2020-01-28 | MEDORE_CR18_JLT | Trakhees approved Dwgs
303 | 2020-01-28 | MEDORE_CR18_JLT | Manpower contract update
304 | 2020-01-28 | MEDORE_CR18_JLT | Sika soft reminder
305 | 2020-01-28 | MEDORE_CR18_JLT | Bitar response Riyaz RCC - IMP
306 | 2020-01-28 | MEDORE_CR18_JLT | Sika submittal link
307 | 2020-01-28 | MEDORE_CR18_JLT | Balance two materials
308 | 2020-01-28 | MEDORE_CR18_JLT | Provide sequence & Response
309 | 2020-01-28 | MEDORE_CR18_JLT | Hamza reply (Sika)
310 | 2020-01-29 | MEDORE_CR18_JLT | AnchorFix-3001
311 | 2020-01-29 | MEDORE_CR18_JLT | Print one book (rev MS)
312 | 2020-01-29 | MEDORE_CR18_JLT | Initial draft programme 5 months
313 | 2020-01-29 | MEDORE_CR18_JLT | Programme to Riyaz
314 | 2020-01-29 | MEDORE_CR18_JLT | Purchase pricing
315 | 2020-01-30 | MEDORE_CR18_JLT | On leave
316 | 2020-01-30 | MEDORE_CR18_JLT | RE-100 and RE-500 tech info
317 | 2020-01-30 | MEDORE_CR18_JLT | Advance letter (sameh)
318 | 2020-01-30 | MEDORE_CR18_JLT | Programme draft
319 | 2020-02-01 | MEDORE_CR18_JLT | Labor supply contract
320 | 2020-02-01 | MEDORE_CR18_JLT | Soft reminder sarath
321 | 2020-02-01 | MEDORE_CR18_JLT | B-4 as-built layout
322 | 2020-02-02 | MEDORE_CR18_JLT | Updated
323 | 2020-02-02 | MEDORE_CR18_JLT | Layout to suleiman (B4-B3)
324 | 2020-02-02 | MEDORE_CR18_JLT | Pls provide B3-B2
325 | 2020-02-02 | MEDORE_CR18_JLT | Follow-up technosteel
326 | 2020-02-02 | MEDORE_CR18_JLT | Layout to suleiman (B3-B2)
327 | 2020-02-02 | MEDORE_CR18_JLT | PT layout drawings (Atef)
328 | 2020-02-03 | MEDORE_CR18_JLT | Crack layout plan
329 | 2020-02-03 | MEDORE_CR18_JLT | Pricing request Fosroc
330 | 2020-02-03 | MEDORE_CR18_JLT | Jamal pricing Qtn
331 | 2020-02-03 | MEDORE_CR18_JLT | Best please
332 | 2020-02-03 | MEDORE_CR18_JLT | Riyaz consultant response email
333 | 2020-02-03 | MEDORE_CR18_JLT | Vertical elements letter (Bitar)
334 | 2020-02-04 | MEDORE_CR18_JLT | Jamal (Fosroc) best price
335 | 2020-02-04 | MEDORE_CR18_JLT | As-built atef
336 | 2020-02-04 | MEDORE_CR18_JLT | Sikacrete 113PP to CCL203
337 | 2020-02-04 | MEDORE_CR18_JLT | Slabs crack layout full
338 | 2020-02-04 | MEDORE_CR18_JLT | Its okay pls print
339 | 2020-02-05 | MEDORE_CR18_JLT | Nithin DM Comment
340 | 2020-02-06 | MEDORE_CR18_JLT | IFC architectural & structural - IMP
341 | 2020-02-06 | MEDORE_CR18_JLT | Make comparison
342 | 2020-02-06 | MEDORE_CR18_JLT | Riyaz request for submissions
343 | 2020-02-06 | MEDORE_CR18_JLT | Omar to Nithin
344 | 2020-02-06 | MEDORE_CR18_JLT | Submittal list to Kurt
345 | 2020-02-06 | MEDORE_CR18_JLT | Provide remaining floors (Suleiman)
346 | 2020-02-06 | MEDORE_CR18_JLT | Kurt updates
347 | 2020-02-06 | MEDORE_CR18_JLT | As-built to Suleiman
348 | 2020-02-06 | MEDORE_CR18_JLT | Bitar to Nithin
349 | 2020-02-06 | MEDORE_CR18_JLT | RFI response to Omar (By riyaz)
350 | 2020-02-06 | MEDORE_CR18_JLT | Omar reply Riyaz
351 | 2020-02-06 | MEDORE_CR18_JLT | Bitar to Riyaz
352 | 2020-02-06 | MEDORE_CR18_JLT | Demolition subcon visit arrange
353 | 2020-02-06 | MEDORE_CR18_JLT | Submittal list to Riyaz
354 | 2020-02-06 | MEDORE_CR18_JLT | Confirmed demolition visit
355 | 2020-02-06 | MEDORE_CR18_JLT | Invoice details
356 | 2020-02-06 | MEDORE_CR18_JLT | Hilti pricing request (Armia)
357 | 2020-02-06 | MEDORE_CR18_JLT | RAFT drawings & calculations
358 | 2020-02-06 | MEDORE_CR18_JLT | Hilti TE50 Qtn
359 | 2020-02-06 | MEDORE_CR18_JLT | Hilti Drill bits quotation
360 | 2020-02-08 | MEDORE_CR18_JLT | Letters for China Railway
361 | 2020-02-09 | MEDORE_CR18_JLT | Reminder from Riyaz
362 | 2020-02-09 | MEDORE_CR18_JLT | Draft warranty for cracks
363 | 2020-02-09 | MEDORE_CR18_JLT | Updated RAFT thickening
364 | 2020-02-09 | MEDORE_CR18_JLT | Submit draft warranty
365 | 2020-02-09 | MEDORE_CR18_JLT | Reminder from Nithin
366 | 2020-02-09 | MEDORE_CR18_JLT | Updated letter Bitar
367 | 2020-02-09 | MEDORE_CR18_JLT | Letters to China Railway
368 | 2020-02-09 | MEDORE_CR18_JLT | Signed contract (Atef)
369 | 2020-02-09 | MEDORE_CR18_JLT | Not as discussed
370 | 2020-02-09 | MEDORE_CR18_JLT | Draft warranty to China Railway
371 | 2020-02-09 | MEDORE_CR18_JLT | Martin clarify
372 | 2020-02-09 | MEDORE_CR18_JLT | Old PDS
373 | 2020-02-09 | MEDORE_CR18_JLT | Commented mat submittal columns
374 | 2020-02-09 | MEDORE_CR18_JLT | 130 to 2pm
375 | 2020-02-09 | MEDORE_CR18_JLT | B3 supporting wall Omar
376 | 2020-02-09 | MEDORE_CR18_JLT | B3 wall issue to Riyaz
377 | 2020-02-09 | MEDORE_CR18_JLT | Charminar labor supply
378 | 2020-02-10 | MEDORE_CR18_JLT | Confirm attendance
379 | 2020-02-10 | MEDORE_CR18_JLT | Confirmed 130pm
380 | 2020-02-10 | MEDORE_CR18_JLT | Draft letter for review
381 | 2020-02-10 | MEDORE_CR18_JLT | Find location pin
382 | 2020-02-10 | MEDORE_CR18_JLT | Invitation for APG meeting
383 | 2020-02-10 | MEDORE_CR18_JLT | Letter specimen
384 | 2020-02-11 | MEDORE_CR18_JLT | Location map APG
385 | 2020-02-11 | MEDORE_CR18_JLT | Meeting invitation Eversendai
386 | 2020-02-11 | MEDORE_CR18_JLT | okay
387 | 2020-02-11 | MEDORE_CR18_JLT | Omar response
388 | 2020-02-11 | MEDORE_CR18_JLT | Send location
389 | 2020-02-11 | MEDORE_CR18_JLT | Sika datasheets Hamza
390 | 2020-02-11 | MEDORE_CR18_JLT | Steel plate drawings Aster
391 | 2020-02-11 | MEDORE_CR18_JLT | Subcon agreement
392 | 2020-02-11 | MEDORE_CR18_JLT | Undertaking letter required
393 | 2020-02-11 | MEDORE_CR18_JLT | Undertaking letter specimen
394 | 2020-02-11 | MEDORE_CR18_JLT | Updates after technical meeting
395 | 2020-02-12 | MEDORE_CR18_JLT | Review CCL letter
396 | 2020-02-12 | MEDORE_CR18_JLT | don't send
397 | 2020-02-12 | MEDORE_CR18_JLT | Original undertaking
398 | 2020-02-12 | MEDORE_CR18_JLT | Fwd details
399 | 2020-02-12 | MEDORE_CR18_JLT | Undertaking letter to Riyaz
400 | 2020-02-12 | MEDORE_CR18_JLT | Draft is okay
401 | 2020-02-12 | MEDORE_CR18_JLT | Find undertaking letter
402 | 2020-02-12 | MEDORE_CR18_JLT | CCL's compliance statement cracks
403 | 2020-02-12 | MEDORE_CR18_JLT | Strengthening schedule
404 | 2020-02-13 | MEDORE_CR18_JLT | Consultant comments 8th floor
405 | 2020-02-13 | MEDORE_CR18_JLT | Mail for omar
406 | 2020-02-13 | MEDORE_CR18_JLT | Email sent Omar
407 | 2020-02-13 | MEDORE_CR18_JLT | MOM CR18 and APG
408 | 2020-02-13 | MEDORE_CR18_JLT | Building permit
409 | 2020-02-13 | MEDORE_CR18_JLT | Different Omar
410 | 2020-02-13 | MEDORE_CR18_JLT | Updated program
411 | 2020-02-13 | MEDORE_CR18_JLT | Confirm attendance
412 | 2020-02-15 | MEDORE_CR18_JLT | Ready-mix Lootah Qtn
413 | 2020-02-15 | MEDORE_CR18_JLT | Strengthening program
414 | 2020-02-16 | MEDORE_CR18_JLT | As-built upper levels
415 | 2020-02-16 | MEDORE_CR18_JLT | Send UB
416 | 2020-02-16 | MEDORE_CR18_JLT | Send GF C8
417 | 2020-02-17 | MEDORE_CR18_JLT | Column rebar in Raft (Riyaz)
418 | 2020-02-17 | MEDORE_CR18_JLT | Upper basement photos
419 | 2020-02-17 | MEDORE_CR18_JLT | Ground floor as-built
420 | 2020-02-17 | MEDORE_CR18_JLT | Remaining surveys
421 | 2020-02-17 | MEDORE_CR18_JLT | UB sent
422 | 2020-02-17 | MEDORE_CR18_JLT | No need L-03
423 | 2020-02-18 | MEDORE_CR18_JLT | Column strengthening drawings (Odai) - IMP
424 | 2020-02-19 | MEDORE_CR18_JLT | Mail to be arranged (Atef)
425 | 2020-02-20 | MEDORE_CR18_JLT | Reminder by Riyaz
426 | 2020-02-20 | MEDORE_CR18_JLT | MS comments column + tendons
427 | 2020-02-20 | MEDORE_CR18_JLT | Submittal list
428 | 2020-02-20 | MEDORE_CR18_JLT | Fill if date missing
429 | 2020-02-22 | MEDORE_CR18_JLT | Email to Riyaz (Sameh)
430 | 2020-02-22 | MEDORE_CR18_JLT | Crack comments (Rev-00)
431 | 2020-02-22 | MEDORE_CR18_JLT | Submittal list
432 | 2020-02-22 | MEDORE_CR18_JLT | Reply to Afsal
433 | 2020-02-22 | MEDORE_CR18_JLT | Submittal list to Riyaz
434 | 2020-02-23 | MEDORE_CR18_JLT | Comments on Mat. Submittal column
435 | 2020-02-23 | MEDORE_CR18_JLT | Create books
436 | 2020-02-23 | MEDORE_CR18_JLT | Send Cutting MS (Manara)
437 | 2020-02-24 | MEDORE_CR18_JLT | Afsal Submittal comments
438 | 2020-02-24 | MEDORE_CR18_JLT | Manara MS
439 | 2020-02-24 | MEDORE_CR18_JLT | Crack & Raft approved
440 | 2020-02-24 | MEDORE_CR18_JLT | Make LPO Fosroc
441 | 2020-02-24 | MEDORE_CR18_JLT | Revised permit
442 | 2020-02-24 | MEDORE_CR18_JLT | Compliance to afsal
443 | 2020-02-24 | MEDORE_CR18_JLT | Send attachment again
444 | 2020-02-25 | MEDORE_CR18_JLT | Jasmine LPO
445 | 2020-02-25 | MEDORE_CR18_JLT | Resubmit GPR MS
446 | 2020-02-25 | MEDORE_CR18_JLT | GPR Compliance
447 | 2020-02-25 | MEDORE_CR18_JLT | LPO to Fosroc
448 | 2020-02-25 | MEDORE_CR18_JLT | Noted - Afsal
449 | 2020-02-25 | MEDORE_CR18_JLT | Latest prequalification required USW
450 | 2020-02-25 | MEDORE_CR18_JLT | Make book for Cutting MS
451 | 2020-02-26 | MEDORE_CR18_JLT | Reminder by Afsal
452 | 2020-02-26 | MEDORE_CR18_JLT | will be submitted today
453 | 2020-02-26 | MEDORE_CR18_JLT | demolition
454 | 2020-02-26 | MEDORE_CR18_JLT | Our MS inlcudes
455 | 2020-02-26 | MEDORE_CR18_JLT | Compliance sheet email
456 | 2020-02-26 | MEDORE_CR18_JLT | USW Prequalification
457 | 2020-02-26 | MEDORE_CR18_JLT | Material available
458 | 2020-02-26 | MEDORE_CR18_JLT | Inspection request sample
459 | 2020-02-26 | MEDORE_CR18_JLT | Cheque copy jamal
460 | 2020-02-26 | MEDORE_CR18_JLT | this time only
461 | 2020-02-26 | MEDORE_CR18_JLT | Letter from CR18 - Programme
462 | 2020-02-27 | MEDORE_CR18_JLT | Meeting updated
463 | 2020-02-27 | MEDORE_CR18_JLT | Noted
464 | 2020-02-27 | MEDORE_CR18_JLT | MOM for progress meeting
465 | 2020-02-27 | MEDORE_CR18_JLT | Wet cracks mockup IR
466 | 2020-02-27 | MEDORE_CR18_JLT | Response to Programme letter
467 | 2020-02-29 | MEDORE_CR18_JLT | Slab strengthening submission
468 | 2020-02-29 | MEDORE_CR18_JLT | Advance required first
469 | 2020-02-29 | MEDORE_CR18_JLT | Committed to support
470 | 2020-03-02 | MEDORE_CR18_JLT | Comments on Crack MS
471 | 2020-03-02 | MEDORE_CR18_JLT | SAFE Model
472 | 2020-03-02 | MEDORE_CR18_JLT | Email to Fosroc
473 | 2020-03-02 | MEDORE_CR18_JLT | Akl response
474 | 2020-03-03 | MEDORE_CR18_JLT | Technical meeting request (Riyaz)
475 | 2020-03-03 | MEDORE_CR18_JLT | Email martin with Questions
476 | 2020-03-03 | MEDORE_CR18_JLT | Hazem to assist
477 | 2020-03-03 | MEDORE_CR18_JLT | Reminder Jamal
478 | 2020-03-03 | MEDORE_CR18_JLT | 8th floor calculations
479 | 2020-03-04 | MEDORE_CR18_JLT | Submittal list sameh
480 | 2020-03-04 | MEDORE_CR18_JLT | Waterproofing team
481 | 2020-03-04 | MEDORE_CR18_JLT | Red clearance
482 | 2020-03-04 | MEDORE_CR18_JLT | Sika question response
483 | 2020-03-04 | MEDORE_CR18_JLT | Jamal (Fosroc) response
484 | 2020-03-04 | MEDORE_CR18_JLT | Send photos again
485 | 2020-03-04 | MEDORE_CR18_JLT | Photos by Atef (Wet cracks)
486 | 2020-03-04 | MEDORE_CR18_JLT | MOM of technical meeting
487 | 2020-03-04 | MEDORE_CR18_JLT | Mock-up for wet cracks
488 | 2020-03-05 | MEDORE_CR18_JLT | Drawing numbering
489 | 2020-03-05 | MEDORE_CR18_JLT | DM regulations
490 | 2020-03-05 | MEDORE_CR18_JLT | Compliance for Cracks MS
491 | 2020-03-05 | MEDORE_CR18_JLT | Crack mock-up comments compliance
492 | 2020-03-05 | MEDORE_CR18_JLT | Meeting confirmation
493 | 2020-03-05 | MEDORE_CR18_JLT | Jamal confirmed
494 | 2020-03-05 | MEDORE_CR18_JLT | Planning engineer meeting
495 | 2020-03-05 | MEDORE_CR18_JLT | IR with APG (Crack mock-up comments)
496 | 2020-03-05 | MEDORE_CR18_JLT | 8th floor drawings
497 | 2020-03-05 | MEDORE_CR18_JLT | Provide coupler submittal
498 | 2020-03-05 | MEDORE_CR18_JLT | Request to claire
499 | 2020-03-05 | MEDORE_CR18_JLT | BRC Coupler Submittal
500 | 2020-03-05 | MEDORE_CR18_JLT | Construction joint request
501 | 2020-03-05 | MEDORE_CR18_JLT | Compliance response
502 | 2020-03-07 | MEDORE_CR18_JLT | 8th to 19th floor
503 | 2020-03-08 | MEDORE_CR18_JLT | Delay of works letter from CR18 - IMP
504 | 2020-03-08 | MEDORE_CR18_JLT | Fwd letter
505 | 2020-03-08 | MEDORE_CR18_JLT | Submission comments Afsal
506 | 2020-03-08 | MEDORE_CR18_JLT | Passenger hoist to Omar CR18
507 | 2020-03-08 | MEDORE_CR18_JLT | Response to Afsal in red
508 | 2020-03-08 | MEDORE_CR18_JLT | Masterkure and Masterbrace
509 | 2020-03-08 | MEDORE_CR18_JLT | Minutes of meeting
510 | 2020-03-08 | MEDORE_CR18_JLT | USW trade license & VAT
511 | 2020-03-08 | MEDORE_CR18_JLT | Reply to Feroz
512 | 2020-03-08 | MEDORE_CR18_JLT | Feroz response and details
513 | 2020-03-08 | MEDORE_CR18_JLT | Mill certificate coupler
514 | 2020-03-08 | MEDORE_CR18_JLT | HY-RIB
515 | 2020-03-08 | MEDORE_CR18_JLT | Response in Green (Afsal)
516 | 2020-03-09 | MEDORE_CR18_JLT | Resubmit Raft MS
517 | 2020-03-09 | MEDORE_CR18_JLT | Advance payment response
518 | 2020-03-09 | MEDORE_CR18_JLT | Coupler submittal print
519 | 2020-03-09 | MEDORE_CR18_JLT | Soft copy also
520 | 2020-03-09 | MEDORE_CR18_JLT | Jamal provide certificates
521 | 2020-03-10 | MEDORE_CR18_JLT | Injection machine certificates
522 | 2020-03-10 | MEDORE_CR18_JLT | Request to Jamal details
523 | 2020-03-10 | MEDORE_CR18_JLT | Zoning sketches
524 | 2020-03-10 | MEDORE_CR18_JLT | Sent to Omar
525 | 2020-03-10 | MEDORE_CR18_JLT | Resubmit cutting MS
526 | 2020-03-10 | MEDORE_CR18_JLT | Steel works contract
527 | 2020-03-10 | MEDORE_CR18_JLT | Hy-rib to Omar
528 | 2020-03-10 | MEDORE_CR18_JLT | Coupler response
529 | 2020-03-10 | MEDORE_CR18_JLT | Pending submissions list
530 | 2020-03-10 | MEDORE_CR18_JLT | Make printout
531 | 2020-03-10 | MEDORE_CR18_JLT | Add paper
532 | 2020-03-11 | MEDORE_CR18_JLT | Column jacketing Code-B
533 | 2020-03-11 | MEDORE_CR18_JLT | Reminder to Jamal
534 | 2020-03-11 | MEDORE_CR18_JLT | Print one more book
535 | 2020-03-11 | MEDORE_CR18_JLT | Send prequal for cutting
536 | 2020-03-11 | MEDORE_CR18_JLT | Crack repair response Atef
537 | 2020-03-11 | MEDORE_CR18_JLT | Make printout
538 | 2020-03-11 | MEDORE_CR18_JLT | Water stopping mortar
539 | 2020-03-11 | MEDORE_CR18_JLT | Advance payment
540 | 2020-03-11 | MEDORE_CR18_JLT | Manara prequalification
541 | 2020-03-11 | MEDORE_CR18_JLT | Atef Fwd
542 | 2020-03-11 | MEDORE_CR18_JLT | CCL Applicator Certificate
543 | 2020-03-11 | MEDORE_CR18_JLT | Steel column CAD required
544 | 2020-03-12 | MEDORE_CR18_JLT | Reply for training certificates
545 | 2020-03-12 | MEDORE_CR18_JLT | Passenger hoist
546 | 2020-03-12 | MEDORE_CR18_JLT | Updated Fosroc training cert
547 | 2020-03-12 | MEDORE_CR18_JLT | Hoist response Omar
548 | 2020-03-12 | MEDORE_CR18_JLT | Afsal reply
549 | 2020-03-12 | MEDORE_CR18_JLT | Make printouts
550 | 2020-03-12 | MEDORE_CR18_JLT | Omar reply Afsal
551 | 2020-03-12 | MEDORE_CR18_JLT | Riyaz reply Omar
552 | 2020-03-12 | MEDORE_CR18_JLT | USW subcontract draft
553 | 2020-03-12 | MEDORE_CR18_JLT | Bitar reply Riyaz Hoist
554 | 2020-03-12 | MEDORE_CR18_JLT | Bitar reply Afsal
555 | 2020-03-12 | MEDORE_CR18_JLT | Afsal reply Omar
556 | 2020-03-12 | MEDORE_CR18_JLT | E-Invoicing Conmix
557 | 2020-03-14 | MEDORE_CR18_JLT | B4 layout and tank
558 | 2020-03-14 | MEDORE_CR18_JLT | Revise & submit - Column & Raft - IMP
559 | 2020-03-14 | MEDORE_CR18_JLT | DM permit conditions
560 | 2020-03-14 | MEDORE_CR18_JLT | Pending submissions list
561 | 2020-03-14 | MEDORE_CR18_JLT | Updated subcontract agreement
562 | 2020-03-14 | MEDORE_CR18_JLT | FYI (pending list)
563 | 2020-03-14 | MEDORE_CR18_JLT | USW subcontract draft to Feroz
564 | 2020-03-14 | MEDORE_CR18_JLT | Digital invoicing
565 | 2020-03-14 | MEDORE_CR18_JLT | Concrete jacketing material Rev & resubmit
566 | 2020-03-14 | MEDORE_CR18_JLT | Feroz USW response
567 | 2020-03-15 | MEDORE_CR18_JLT | Delays in Engg submission
568 | 2020-03-15 | MEDORE_CR18_JLT | Inspection checklist
569 | 2020-03-15 | MEDORE_CR18_JLT | CAD drawings for USW required
570 | 2020-03-15 | MEDORE_CR18_JLT | CAD drawings to USW sent
571 | 2020-03-15 | MEDORE_CR18_JLT | Thanks
572 | 2020-03-15 | MEDORE_CR18_JLT | Drawings & calculation comments
573 | 2020-03-15 | MEDORE_CR18_JLT | Subcontract agreement USW
574 | 2020-03-15 | MEDORE_CR18_JLT | Updated
575 | 2020-03-15 | MEDORE_CR18_JLT | Cutting & Scanning submittal Code-B
576 | 2020-03-15 | MEDORE_CR18_JLT | Drawing comments Fwd Omar
577 | 2020-03-15 | MEDORE_CR18_JLT | CEO meeting required
578 | 2020-03-15 | MEDORE_CR18_JLT | Fosroc CCL training certificate
579 | 2020-03-15 | MEDORE_CR18_JLT | Send numbering system
580 | 2020-03-15 | MEDORE_CR18_JLT | Thanks
581 | 2020-03-15 | MEDORE_CR18_JLT | Thanks for invite USW
582 | 2020-03-15 | MEDORE_CR18_JLT | Pull-out test results - Past
583 | 2020-03-15 | MEDORE_CR18_JLT | Drawing numbering
584 | 2020-03-15 | MEDORE_CR18_JLT | Column str
585 | 2020-03-15 | MEDORE_CR18_JLT | Structural query
586 | 2020-03-15 | MEDORE_CR18_JLT | Wet cracks site report
587 | 2020-03-16 | MEDORE_CR18_JLT | List of numbering
588 | 2020-03-16 | MEDORE_CR18_JLT | CCL submission list
589 | 2020-03-16 | MEDORE_CR18_JLT | Pull-out test results -Fwd
590 | 2020-03-16 | MEDORE_CR18_JLT | Material requirement
591 | 2020-03-16 | MEDORE_CR18_JLT | Commented RFIs
592 | 2020-03-16 | MEDORE_CR18_JLT | Proposed numbering Omar
593 | 2020-03-16 | MEDORE_CR18_JLT | Pull-out test request Sika
594 | 2020-03-16 | MEDORE_CR18_JLT | Numbering ok
595 | 2020-03-16 | MEDORE_CR18_JLT | BARTEC letter request Samuil BRC
596 | 2020-03-16 | MEDORE_CR18_JLT | Conmix Qtn RecCon MC5mm 12AED
597 | 2020-03-16 | MEDORE_CR18_JLT | Conmix Qtn fwd
598 | 2020-03-16 | MEDORE_CR18_JLT | Approved PT drawings
599 | 2020-03-16 | MEDORE_CR18_JLT | Anchor Fix-2 pull-out test results ref
600 | 2020-03-16 | MEDORE_CR18_JLT | Afsal reply Omar
601 | 2020-03-16 | MEDORE_CR18_JLT | B4 slab
602 | 2020-03-16 | MEDORE_CR18_JLT | Column Strengthening Drawings
603 | 2020-03-16 | MEDORE_CR18_JLT | RAFT thickening Drawings
604 | 2020-03-16 | MEDORE_CR18_JLT | Reply CR18
605 | 2020-03-16 | MEDORE_CR18_JLT | Kurt make submittal prints
606 | 2020-03-16 | MEDORE_CR18_JLT | Send core results
607 | 2020-03-16 | MEDORE_CR18_JLT | Results sent
608 | 2020-03-16 | MEDORE_CR18_JLT | Steel corrosion response request
609 | 2020-03-17 | MEDORE_CR18_JLT | USW signed agreement
610 | 2020-03-17 | MEDORE_CR18_JLT | Email hazma for pull-out
611 | 2020-03-17 | MEDORE_CR18_JLT | Make LPO for sika
612 | 2020-03-17 | MEDORE_CR18_JLT | Sika LPO to Martin
613 | 2020-03-17 | MEDORE_CR18_JLT | Afsal to Omar for Dwgs
614 | 2020-03-17 | MEDORE_CR18_JLT | BARTEC Coupler Letter
615 | 2020-03-17 | MEDORE_CR18_JLT | PDF to CR18
616 | 2020-03-17 | MEDORE_CR18_JLT | Stengulf quotation
617 | 2020-03-17 | MEDORE_CR18_JLT | Columns Rev-02 material submittal
618 | 2020-03-17 | MEDORE_CR18_JLT | Make separate CAD and PDf
619 | 2020-03-17 | MEDORE_CR18_JLT | Noted
620 | 2020-03-17 | MEDORE_CR18_JLT | E-Invoice
621 | 2020-03-18 | MEDORE_CR18_JLT | MS for pull-out required
622 | 2020-03-18 | MEDORE_CR18_JLT | GA comments
623 | 2020-03-18 | MEDORE_CR18_JLT | Omar reply GA comments
624 | 2020-03-18 | MEDORE_CR18_JLT | List of Drawing numbering
625 | 2020-03-18 | MEDORE_CR18_JLT | Bitar reply
626 | 2020-03-18 | MEDORE_CR18_JLT | RFIs fwd Sameh
627 | 2020-03-18 | MEDORE_CR18_JLT | RCC partition wall Fwd
628 | 2020-03-18 | MEDORE_CR18_JLT | Approved PT Fwd
629 | 2020-03-18 | MEDORE_CR18_JLT | Look ahead Fwd
630 | 2020-03-18 | MEDORE_CR18_JLT | Drawing numbering
631 | 2020-03-18 | MEDORE_CR18_JLT | 13th to 19th floor
632 | 2020-03-18 | MEDORE_CR18_JLT | Drawing numbering
633 | 2020-03-18 | MEDORE_CR18_JLT | Noted
634 | 2020-03-18 | MEDORE_CR18_JLT | Delay of works response Letter
635 | 2020-03-18 | MEDORE_CR18_JLT | Technosteel follow-up
636 | 2020-03-19 | MEDORE_CR18_JLT | C2 Column at GF
637 | 2020-03-19 | MEDORE_CR18_JLT | MAR from USW
638 | 2020-03-19 | MEDORE_CR18_JLT | Mat submittal reply to USW
639 | 2020-03-19 | MEDORE_CR18_JLT | E-Invoice
640 | 2020-03-19 | MEDORE_CR18_JLT | Site report by Nageh - Leakage
641 | 2020-03-21 | MEDORE_CR18_JLT | Works program update
642 | 2020-03-21 | MEDORE_CR18_JLT | Pull-out test MS from Sika
643 | 2020-03-21 | MEDORE_CR18_JLT | Pls update program
644 | 2020-03-21 | MEDORE_CR18_JLT | Crack layout update
645 | 2020-03-21 | MEDORE_CR18_JLT | Updated material submittal USW
646 | 2020-03-22 | MEDORE_CR18_JLT | Submit Hard copies USW
647 | 2020-03-22 | MEDORE_CR18_JLT | Will be done
648 | 2020-03-22 | MEDORE_CR18_JLT | Resubmit Steel Cleaning MS (comments)
649 | 2020-03-22 | MEDORE_CR18_JLT | Pull-out prints
650 | 2020-03-22 | MEDORE_CR18_JLT | Pull-out load values Sika
651 | 2020-03-22 | MEDORE_CR18_JLT | Response for Afsal (To Sameh)
652 | 2020-03-22 | MEDORE_CR18_JLT | Sameh reply Afsal
653 | 2020-03-22 | MEDORE_CR18_JLT | Workshop meeting
654 | 2020-03-22 | MEDORE_CR18_JLT | Raft thickening MS approved
655 | 2020-03-22 | MEDORE_CR18_JLT | Crack layout first
656 | 2020-03-22 | MEDORE_CR18_JLT | Steel plates cover sheet
657 | 2020-03-22 | MEDORE_CR18_JLT | Corrosion inhibition Conmix
658 | 2020-03-22 | MEDORE_CR18_JLT | Thanks send balance
659 | 2020-03-22 | MEDORE_CR18_JLT | Corrosion inhibition Sika
660 | 2020-03-22 | MEDORE_CR18_JLT | B3 and B4 also
661 | 2020-03-22 | MEDORE_CR18_JLT | Pull-out test document Sika
662 | 2020-03-22 | MEDORE_CR18_JLT | Send officially
663 | 2020-03-22 | MEDORE_CR18_JLT | Updated layout
664 | 2020-03-22 | MEDORE_CR18_JLT | Kurt make print
665 | 2020-03-22 | MEDORE_CR18_JLT | Submission log (CR18)
666 | 2020-03-22 | MEDORE_CR18_JLT | Review attached
667 | 2020-03-22 | MEDORE_CR18_JLT | Print 2 copies
668 | 2020-03-22 | MEDORE_CR18_JLT | Corrosion inhibition Conmix mail
669 | 2020-03-22 | MEDORE_CR18_JLT | Corrosion inhibition Sika mail
670 | 2020-03-22 | MEDORE_CR18_JLT | Email conmix further
671 | 2020-03-23 | MEDORE_CR18_JLT | Murugesan response
672 | 2020-03-23 | MEDORE_CR18_JLT | Comments for steel mat submittal
673 | 2020-03-23 | MEDORE_CR18_JLT | Resubmit column jacketing material
674 | 2020-03-23 | MEDORE_CR18_JLT | DCL + Sample required USW
675 | 2020-03-23 | MEDORE_CR18_JLT | Request VAT
676 | 2020-03-23 | MEDORE_CR18_JLT | Sent VAT
677 | 2020-03-23 | MEDORE_CR18_JLT | Prequalification hard-copy USW
678 | 2020-03-23 | MEDORE_CR18_JLT | Afsal response
679 | 2020-03-23 | MEDORE_CR18_JLT | Prequalification also
680 | 2020-03-23 | MEDORE_CR18_JLT | By tomorrow
681 | 2020-03-23 | MEDORE_CR18_JLT | Received VAT
682 | 2020-03-24 | MEDORE_CR18_JLT | ARIES 3rd party certificate
683 | 2020-03-24 | MEDORE_CR18_JLT | Reminder on program
684 | 2020-03-24 | MEDORE_CR18_JLT | Discrepancy
685 | 2020-03-24 | MEDORE_CR18_JLT | Not relevant to CCL
686 | 2020-03-24 | MEDORE_CR18_JLT | Hard copies required from USW
687 | 2020-03-24 | MEDORE_CR18_JLT | Full strengthening drawings B3, B2, LB
688 | 2020-03-25 | MEDORE_CR18_JLT | Column cover issue & photos
689 | 2020-03-26 | MEDORE_CR18_JLT | Make submittal
690 | 2020-03-26 | MEDORE_CR18_JLT | Need soft copy as well
691 | 2020-03-26 | MEDORE_CR18_JLT | Download link for soft copy
692 | 2020-03-26 | MEDORE_CR18_JLT | Shotcrete strength maximum
693 | 2020-03-26 | MEDORE_CR18_JLT | Crack injection letter
694 | 2020-03-26 | MEDORE_CR18_JLT | Make CD
695 | 2020-03-26 | MEDORE_CR18_JLT | Updated program atef
696 | 2020-03-26 | MEDORE_CR18_JLT | Ref for project specs
697 | 2020-03-26 | MEDORE_CR18_JLT | Urgently required USW
698 | 2020-03-29 | MEDORE_CR18_JLT | Chipping cost calc
699 | 2020-03-29 | MEDORE_CR18_JLT | Crack injection letter from CR18
700 | 2020-03-29 | MEDORE_CR18_JLT | Make CD steel MS
701 | 2020-03-29 | MEDORE_CR18_JLT | Delay in str. Submission CR18
702 | 2020-03-29 | MEDORE_CR18_JLT | MS column steel jacketing
703 | 2020-03-29 | MEDORE_CR18_JLT | Additional cracks response letter
704 | 2020-03-29 | MEDORE_CR18_JLT | Delay response letter
705 | 2020-03-29 | MEDORE_CR18_JLT | Updated program to atef
706 | 2020-03-29 | MEDORE_CR18_JLT | Update submission dates
707 | 2020-03-30 | MEDORE_CR18_JLT | Updated program to Riyaz
708 | 2020-03-30 | MEDORE_CR18_JLT | Sample board today USW
709 | 2020-03-30 | MEDORE_CR18_JLT | AnchorFix-3001 as replacement
710 | 2020-03-30 | MEDORE_CR18_JLT | Back-propping layout required
711 | 2020-03-30 | MEDORE_CR18_JLT | Str. Drawings to Suleiman CR18
712 | 2020-03-30 | MEDORE_CR18_JLT | Locally around columns
713 | 2020-03-30 | MEDORE_CR18_JLT | FYI - slab opening drawings
714 | 2020-03-30 | MEDORE_CR18_JLT | Column jacketing compliance
715 | 2020-03-30 | MEDORE_CR18_JLT | B4 layout query from CR18
716 | 2020-03-30 | MEDORE_CR18_JLT | 8th floor PT
717 | 2020-03-30 | MEDORE_CR18_JLT | Already sent
718 | 2020-03-30 | MEDORE_CR18_JLT | Sent but need updates
719 | 2020-03-30 | MEDORE_CR18_JLT | Crack layout for additional cracks
720 | 2020-03-30 | MEDORE_CR18_JLT | Letter of declaration USW
721 | 2020-03-30 | MEDORE_CR18_JLT | Updated compliance
722 | 2020-03-31 | MEDORE_CR18_JLT | B4 layout to be asked
723 | 2020-03-31 | MEDORE_CR18_JLT | B4 layout query to Afsal
724 | 2020-03-31 | MEDORE_CR18_JLT | Additional cracks layout email ref
725 | 2020-03-31 | MEDORE_CR18_JLT | Additional crack new letter from CR18
726 | 2020-03-31 | MEDORE_CR18_JLT | Arrange comparison sheet
727 | 2020-03-31 | MEDORE_CR18_JLT | Back-propping jacks capacity req
728 | 2020-03-31 | MEDORE_CR18_JLT | Pull-out chart clarification
729 | 2020-03-31 | MEDORE_CR18_JLT | AnchorFix-3001 pricing Sika
730 | 2020-03-31 | MEDORE_CR18_JLT | Afsal PT comments
731 | 2020-03-31 | MEDORE_CR18_JLT | Omar reply to Afsal on PT comments
732 | 2020-03-31 | MEDORE_CR18_JLT | New Delay letter
733 | 2020-03-31 | MEDORE_CR18_JLT | Sika conformity letter
734 | 2020-03-31 | MEDORE_CR18_JLT | Approved bonding agent Nitobond EP
735 | 2020-03-31 | MEDORE_CR18_JLT | Fosroc letter to Afsal
736 | 2020-03-31 | MEDORE_CR18_JLT | Compatibility of ReCon MC5mm with EP
737 | 2020-03-31 | MEDORE_CR18_JLT | Certificates required
738 | 2020-03-31 | MEDORE_CR18_JLT | Conmix compatibility response
739 | 2020-03-31 | MEDORE_CR18_JLT | Afsal sent consultant
740 | 2020-03-31 | MEDORE_CR18_JLT | PT comments reply
741 | 2020-04-01 | MEDORE_CR18_JLT | Comments given revise
742 | 2020-04-01 | MEDORE_CR18_JLT | 2 Ton capacity
743 | 2020-04-01 | MEDORE_CR18_JLT | Capacity sketch
744 | 2020-04-01 | MEDORE_CR18_JLT | Clarify email
745 | 2020-04-01 | MEDORE_CR18_JLT | B4 details
746 | 2020-04-01 | MEDORE_CR18_JLT | DM approval help
747 | 2020-04-01 | MEDORE_CR18_JLT | Reminder Sika Hamza
748 | 2020-04-01 | MEDORE_CR18_JLT | Pull-out test MS APPROVAL
749 | 2020-04-01 | MEDORE_CR18_JLT | Hamza noted
750 | 2020-04-01 | MEDORE_CR18_JLT | B4 details to Omar
751 | 2020-04-01 | MEDORE_CR18_JLT | Back-propping fwd Omar
752 | 2020-04-01 | MEDORE_CR18_JLT | Omar reply (further details req)
753 | 2020-04-01 | MEDORE_CR18_JLT | 2T is small
754 | 2020-04-01 | MEDORE_CR18_JLT | B4 layout from Suleiman to Atef
755 | 2020-04-01 | MEDORE_CR18_JLT | Meeting request letter
756 | 2020-04-01 | MEDORE_CR18_JLT | Wet crack mock-up APPROVAL
757 | 2020-04-01 | MEDORE_CR18_JLT | Micro-concrete bonding agent Conmix
758 | 2020-04-02 | MEDORE_CR18_JLT | Calibration + certificate Sika
759 | 2020-04-02 | MEDORE_CR18_JLT | CR18 stamp for drawings
760 | 2020-04-02 | MEDORE_CR18_JLT | Column jacketing Rev03 response
761 | 2020-04-02 | MEDORE_CR18_JLT | PT Works MS APPROVAL
762 | 2020-04-02 | MEDORE_CR18_JLT | Back-propping details
763 | 2020-04-02 | MEDORE_CR18_JLT | Pull-out test
764 | 2020-04-02 | MEDORE_CR18_JLT | Back-propping to Afsal
765 | 2020-04-02 | MEDORE_CR18_JLT | MS GPR Scanning APPROVAL
766 | 2020-04-02 | MEDORE_CR18_JLT | Status of IRs
767 | 2020-04-02 | MEDORE_CR18_JLT | Minutes of Meeting
768 | 2020-04-02 | MEDORE_CR18_JLT | Atef details to Suleiman
769 | 2020-04-02 | MEDORE_CR18_JLT | SAFE model to Afsal
770 | 2020-04-02 | MEDORE_CR18_JLT | IR status reply
771 | 2020-04-05 | MEDORE_CR18_JLT | USW proforma invoice
772 | 2020-04-05 | MEDORE_CR18_JLT | COVID19 permit related email
773 | 2020-04-06 | MEDORE_CR18_JLT | Riyaz response
774 | 2020-04-06 | MEDORE_CR18_JLT | Submission status from CR18
775 | 2020-04-06 | MEDORE_CR18_JLT | Reply to Safeer USW
776 | 2020-04-06 | MEDORE_CR18_JLT | Suleiman B4 to Afsal
777 | 2020-04-06 | MEDORE_CR18_JLT | Can proceed
778 | 2020-04-06 | MEDORE_CR18_JLT | Noted - USW
779 | 2020-04-06 | MEDORE_CR18_JLT | Wise decision
780 | 2020-04-07 | MEDORE_CR18_JLT | Fwd
781 | 2020-04-07 | MEDORE_CR18_JLT | Dwgs reply sugin
782 | 2020-04-07 | MEDORE_CR18_JLT | Provide confirmation
783 | 2020-04-07 | MEDORE_CR18_JLT | Need slab drawings
784 | 2020-04-07 | MEDORE_CR18_JLT | CCL submission status
785 | 2020-04-07 | MEDORE_CR18_JLT | slab drawings to Sugin
786 | 2020-04-07 | MEDORE_CR18_JLT | Thanks
787 | 2020-04-07 | MEDORE_CR18_JLT | RAFT file
788 | 2020-04-07 | MEDORE_CR18_JLT | Will reply
789 | 2020-04-07 | MEDORE_CR18_JLT | Sent yesterday
790 | 2020-04-07 | MEDORE_CR18_JLT | Proposed sump pit
791 | 2020-04-07 | MEDORE_CR18_JLT | Bitar reply afsal about delay letters
792 | 2020-04-07 | MEDORE_CR18_JLT | FYI
793 | 2020-04-08 | MEDORE_CR18_JLT | Afsal reply bitar
794 | 2020-04-08 | MEDORE_CR18_JLT | Inspection request B2 & B3
795 | 2020-04-08 | MEDORE_CR18_JLT | Bitar reply afsal again
796 | 2020-04-08 | MEDORE_CR18_JLT | Letter bitar for review
797 | 2020-04-08 | MEDORE_CR18_JLT | Advance info Conmix
798 | 2020-04-08 | MEDORE_CR18_JLT | Upper basement to Level-07 as-built openings
799 | 2020-04-08 | MEDORE_CR18_JLT | Tell CR18 to put in CC
800 | 2020-04-09 | MEDORE_CR18_JLT | Omar reply afsal
801 | 2020-04-09 | MEDORE_CR18_JLT | Update the BOQ
802 | 2020-04-09 | MEDORE_CR18_JLT | Approval status
803 | 2020-04-11 | MEDORE_CR18_JLT | Revised program
804 | 2020-04-12 | MEDORE_CR18_JLT | Zoom meeting link
805 | 2020-04-12 | MEDORE_CR18_JLT | Safeer about approvals from USW
806 | 2020-04-12 | MEDORE_CR18_JLT | Which link
807 | 2020-04-12 | MEDORE_CR18_JLT | Reminder - reports
808 | 2020-04-12 | MEDORE_CR18_JLT | B3, B2, LB drawings
809 | 2020-04-12 | MEDORE_CR18_JLT | Arrange submission
810 | 2020-04-12 | MEDORE_CR18_JLT | Update program
811 | 2020-04-13 | MEDORE_CR18_JLT | Calculation B3, B2 and LB
812 | 2020-04-13 | MEDORE_CR18_JLT | Material forecast
813 | 2020-04-13 | MEDORE_CR18_JLT | Column XREF
814 | 2020-04-13 | MEDORE_CR18_JLT | Check directly with CR18
815 | 2020-04-13 | MEDORE_CR18_JLT | Pull-out test report
816 | 2020-04-13 | MEDORE_CR18_JLT | Program to Atef
817 | 2020-04-14 | MEDORE_CR18_JLT | Any updates - Safeer USW
818 | 2020-04-14 | MEDORE_CR18_JLT | Atef reply Salim steel cleaning
819 | 2020-04-14 | MEDORE_CR18_JLT | MS fwd by Bitar
820 | 2020-04-14 | MEDORE_CR18_JLT | Update program
821 | 2020-04-14 | MEDORE_CR18_JLT | Revised drawings title
822 | 2020-04-14 | MEDORE_CR18_JLT | Letter response from CR18 additional
823 | 2020-04-14 | MEDORE_CR18_JLT | Column strengthening drawings
824 | 2020-04-14 | MEDORE_CR18_JLT | Joshy reply (Rebar) to CR18
825 | 2020-04-15 | MEDORE_CR18_JLT | Afsal reply joshy
826 | 2020-04-15 | MEDORE_CR18_JLT | Joshy response
827 | 2020-04-15 | MEDORE_CR18_JLT | Old LPO
828 | 2020-04-15 | MEDORE_CR18_JLT | No change in drawing frame
829 | 2020-04-15 | MEDORE_CR18_JLT | LPO Fwd
830 | 2020-04-15 | MEDORE_CR18_JLT | Work ongoing
831 | 2020-04-15 | MEDORE_CR18_JLT | Compliance statement
832 | 2020-04-15 | MEDORE_CR18_JLT | L8-19 drawings
833 | 2020-04-15 | MEDORE_CR18_JLT | Update comments
834 | 2020-04-15 | MEDORE_CR18_JLT | Steel company approvals
835 | 2020-04-15 | MEDORE_CR18_JLT | Dextra Rebar Approval
836 | 2020-04-15 | MEDORE_CR18_JLT | Letter to Mr. Roland
837 | 2020-04-15 | MEDORE_CR18_JLT | Go ahead
838 | 2020-04-15 | MEDORE_CR18_JLT | Updated compliance
839 | 2020-04-15 | MEDORE_CR18_JLT | Letter to Afsal
840 | 2020-04-15 | MEDORE_CR18_JLT | Compliance to Afsal
841 | 2020-04-15 | MEDORE_CR18_JLT | Tower crane tie load
842 | 2020-04-16 | MEDORE_CR18_JLT | Fwd to Omar
843 | 2020-04-16 | MEDORE_CR18_JLT | 3rd party requirements
844 | 2020-04-16 | MEDORE_CR18_JLT | Tower crane response Omar
845 | 2020-04-16 | MEDORE_CR18_JLT | Noted
846 | 2020-04-16 | MEDORE_CR18_JLT | Steel MS Approved
847 | 2020-04-16 | MEDORE_CR18_JLT | Scope of 3rd party (bitar)
848 | 2020-04-16 | MEDORE_CR18_JLT | Compliance for steel guys
849 | 2020-04-16 | MEDORE_CR18_JLT | Column stability from Chipping letter
850 | 2020-04-16 | MEDORE_CR18_JLT | DM approval for modifications letter
851 | 2020-04-16 | MEDORE_CR18_JLT | Resubmit only code C
852 | 2020-04-16 | MEDORE_CR18_JLT | Afsal to Omar Bitar
853 | 2020-04-16 | MEDORE_CR18_JLT | Omar reply sika dowels
854 | 2020-04-18 | MEDORE_CR18_JLT | 7th floor column issues
855 | 2020-04-18 | MEDORE_CR18_JLT | APG reply for column str
856 | 2020-04-18 | MEDORE_CR18_JLT | Program reminder
857 | 2020-04-18 | MEDORE_CR18_JLT | Additional works response letter CR18
858 | 2020-04-18 | MEDORE_CR18_JLT | Backpropping Dwg required
859 | 2020-04-18 | MEDORE_CR18_JLT | Visual survey inspection requests
860 | 2020-04-18 | MEDORE_CR18_JLT | Updated program to CR18
861 | 2020-04-19 | MEDORE_CR18_JLT | Reminder by Afsal to Omar
862 | 2020-04-19 | MEDORE_CR18_JLT | Drawings for printing
863 | 2020-04-19 | MEDORE_CR18_JLT | Send soft copy only
864 | 2020-04-19 | MEDORE_CR18_JLT | 5th floor as-built (Suleiman query)
865 | 2020-04-19 | MEDORE_CR18_JLT | They may break
866 | 2020-04-19 | MEDORE_CR18_JLT | Detailed L8-19 for DM
867 | 2020-04-19 | MEDORE_CR18_JLT | Previous undertaking letter for DM
868 | 2020-04-19 | MEDORE_CR18_JLT | Missing info (afsal to omar)
869 | 2020-04-19 | MEDORE_CR18_JLT | Requsting RAM and Etabs
870 | 2020-04-19 | MEDORE_CR18_JLT | Bitar reply Afsal
871 | 2020-04-19 | MEDORE_CR18_JLT | Email Sajjid (USW) with Mat. Comments
872 | 2020-04-19 | MEDORE_CR18_JLT | 7th floor col comments bitar
873 | 2020-04-19 | MEDORE_CR18_JLT | RAM model by Omar to Afsal
874 | 2020-04-19 | MEDORE_CR18_JLT | Noted
875 | 2020-04-19 | MEDORE_CR18_JLT | When to send etabs
876 | 2020-04-19 | MEDORE_CR18_JLT | Column jacketing material approval
877 | 2020-04-19 | MEDORE_CR18_JLT | Action from USW
878 | 2020-04-19 | MEDORE_CR18_JLT | Spoke to Engr Ahmed
879 | 2020-04-20 | MEDORE_CR18_JLT | Proposed Letter Response Bitar
880 | 2020-04-20 | MEDORE_CR18_JLT | Updated ETABS model
881 | 2020-04-20 | MEDORE_CR18_JLT | Updated Drawings Omar
882 | 2020-04-20 | MEDORE_CR18_JLT | Letter response - Additional works
883 | 2020-04-20 | MEDORE_CR18_JLT | Letter response - Structural stability
884 | 2020-04-20 | MEDORE_CR18_JLT | Letter response - Difference DM Drawings
885 | 2020-04-20 | MEDORE_CR18_JLT | can I forward etabs
886 | 2020-04-20 | MEDORE_CR18_JLT | after final approval
887 | 2020-04-20 | MEDORE_CR18_JLT | Noted
888 | 2020-04-20 | MEDORE_CR18_JLT | UB to 7th floor delay letter from CR18
889 | 2020-04-21 | MEDORE_CR18_JLT | RAFT consultant reply
890 | 2020-04-21 | MEDORE_CR18_JLT | Omar reply afsal
891 | 2020-04-21 | MEDORE_CR18_JLT | Send clearly
892 | 2020-04-21 | MEDORE_CR18_JLT | Clearly explain
893 | 2020-04-21 | MEDORE_CR18_JLT | Noted
894 | 2020-04-21 | MEDORE_CR18_JLT | You can use 3 Ton - Props
895 | 2020-04-21 | MEDORE_CR18_JLT | Tower crane support
896 | 2020-04-21 | MEDORE_CR18_JLT | Needs to be in drawings (bitar)
897 | 2020-04-21 | MEDORE_CR18_JLT | Provide typical details (afsal)
898 | 2020-04-21 | MEDORE_CR18_JLT | Wait DM approval (bitar)
899 | 2020-04-21 | MEDORE_CR18_JLT | Noted
900 | 2020-04-21 | MEDORE_CR18_JLT | Noted too
901 | 2020-04-21 | MEDORE_CR18_JLT | RAFT submission latest
902 | 2020-04-21 | MEDORE_CR18_JLT | CCL commented drawings list
903 | 2020-04-21 | MEDORE_CR18_JLT | Raft Drawings Rev03
904 | 2020-04-21 | MEDORE_CR18_JLT | Structural stability letter (CR18)
905 | 2020-04-21 | MEDORE_CR18_JLT | Additional variation letter (CR18)
906 | 2020-04-21 | MEDORE_CR18_JLT | Noted
907 | 2020-04-21 | MEDORE_CR18_JLT | Put in writing
908 | 2020-04-21 | MEDORE_CR18_JLT | Bitar reply salim (for letter)
909 | 2020-04-22 | MEDORE_CR18_JLT | Third party related comments
910 | 2020-04-22 | MEDORE_CR18_JLT | Wet cracks survey
911 | 2020-04-22 | MEDORE_CR18_JLT | Wet cracks survey to Atef
912 | 2020-04-22 | MEDORE_CR18_JLT | Bitar reply Afsal (3rd party comments)
913 | 2020-04-22 | MEDORE_CR18_JLT | Try numbers
914 | 2020-04-22 | MEDORE_CR18_JLT | Omar reply BV comments
915 | 2020-04-22 | MEDORE_CR18_JLT | Letters Fwd with Bitar response
916 | 2020-04-22 | MEDORE_CR18_JLT | UB to 7th floor comments
917 | 2020-04-22 | MEDORE_CR18_JLT | Remodelling existing slabs
918 | 2020-04-22 | MEDORE_CR18_JLT | Consultant comments column str Rev02
919 | 2020-04-22 | MEDORE_CR18_JLT | No changes on drawings
920 | 2020-04-22 | MEDORE_CR18_JLT | As a formality
921 | 2020-04-23 | MEDORE_CR18_JLT | Corrosion protection MS & Mat Approval
922 | 2020-04-23 | MEDORE_CR18_JLT | UB to 7th floor comments - CCL reply
923 | 2020-04-23 | MEDORE_CR18_JLT | Structural stability letter - CCL reply
924 | 2020-04-23 | MEDORE_CR18_JLT | Updated column strengthening
925 | 2020-04-23 | MEDORE_CR18_JLT | Additional variation - CCL reply
926 | 2020-04-23 | MEDORE_CR18_JLT | Column Str Mat submittal Approval
927 | 2020-04-23 | MEDORE_CR18_JLT | Commented list
928 | 2020-04-23 | MEDORE_CR18_JLT | Its old
929 | 2020-04-23 | MEDORE_CR18_JLT | Column drawings + ETABS
930 | 2020-04-23 | MEDORE_CR18_JLT | Confirmed its same
931 | 2020-04-23 | MEDORE_CR18_JLT | Suleiman to Afsal
932 | 2020-04-23 | MEDORE_CR18_JLT | Wet crack layout updated
933 | 2020-04-23 | MEDORE_CR18_JLT | Latest wet crack layout
934 | 2020-04-23 | MEDORE_CR18_JLT | Passenger hoist comments
935 | 2020-04-23 | MEDORE_CR18_JLT | Will let you know
936 | 2020-04-24 | MEDORE_CR18_JLT | Sequence of column casting
937 | 2020-04-24 | MEDORE_CR18_JLT | Revised target program
938 | 2020-04-25 | MEDORE_CR18_JLT | Site survey for wall - Suleiman
939 | 2020-04-25 | MEDORE_CR18_JLT | Photos & Section details
940 | 2020-04-26 | MEDORE_CR18_JLT | Back-propping plan
941 | 2020-04-26 | MEDORE_CR18_JLT | Rebar cover response
942 | 2020-04-26 | MEDORE_CR18_JLT | B3 and B2 only
943 | 2020-04-26 | MEDORE_CR18_JLT | Back-propping to CR18
944 | 2020-04-26 | MEDORE_CR18_JLT | Afsal to Mohammad of BV
945 | 2020-04-26 | MEDORE_CR18_JLT | 8th to 19th Afsal to BV
946 | 2020-04-26 | MEDORE_CR18_JLT | CCL confirm
947 | 2020-04-26 | MEDORE_CR18_JLT | Invitation
948 | 2020-04-26 | MEDORE_CR18_JLT | Combine crack survey layout
949 | 2020-04-26 | MEDORE_CR18_JLT | Combine crack survey layout
950 | 2020-04-27 | MEDORE_CR18_JLT | Concrete cover Consultant comments
951 | 2020-04-27 | MEDORE_CR18_JLT | Add them to meeting
952 | 2020-04-27 | MEDORE_CR18_JLT | Update request to Sugin USW
953 | 2020-04-27 | MEDORE_CR18_JLT | Cost of edge treatment
954 | 2020-04-27 | MEDORE_CR18_JLT | Passenger hoist reply by bitar
955 | 2020-04-27 | MEDORE_CR18_JLT | Shop drawing template
956 | 2020-04-28 | MEDORE_CR18_JLT | Call in office
957 | 2020-04-28 | MEDORE_CR18_JLT | UB to 7th floor slab study to Afsal
958 | 2020-04-28 | MEDORE_CR18_JLT | Title block to Sugin - USW
959 | 2020-04-28 | MEDORE_CR18_JLT | Raft design drawing & calc Approval
960 | 2020-04-28 | MEDORE_CR18_JLT | Columns design drawing & calc Approval
961 | 2020-04-28 | MEDORE_CR18_JLT | Comment 4 responded
962 | 2020-04-28 | MEDORE_CR18_JLT | Price required
963 | 2020-04-28 | MEDORE_CR18_JLT | Raft & Column approval
964 | 2020-04-28 | MEDORE_CR18_JLT | Commence work from 7th floor
965 | 2020-04-28 | MEDORE_CR18_JLT | Conmix Recon zinc price 225 per 5ltr
966 | 2020-04-29 | MEDORE_CR18_JLT | Crack IR approved
967 | 2020-04-29 | MEDORE_CR18_JLT | Make LPO for Conmix
968 | 2020-04-30 | MEDORE_CR18_JLT | LPO to Muru Conmix Recon Zinc
969 | 2020-04-30 | MEDORE_CR18_JLT | Fwd Vanessa
970 | 2020-04-30 | MEDORE_CR18_JLT | Qtn breakdown format
971 | 2020-04-30 | MEDORE_CR18_JLT | Qtn breakdown format Riyaz
972 | 2020-04-30 | MEDORE_CR18_JLT | Steel cleaning mockup IR
973 | 2020-04-30 | MEDORE_CR18_JLT | Invoicing BOQ
974 | 2020-04-30 | MEDORE_CR18_JLT | Raft drawings
975 | 2020-05-02 | MEDORE_CR18_JLT | Update program of works
976 | 2020-05-02 | MEDORE_CR18_JLT | Nageh site report wet cracks
977 | 2020-05-03 | MEDORE_CR18_JLT | Design comments response CR18
978 | 2020-05-03 | MEDORE_CR18_JLT | Invoicing BOQ
979 | 2020-05-04 | MEDORE_CR18_JLT | Undertaking for BV approval
980 | 2020-05-04 | MEDORE_CR18_JLT | Tank walls - Suleiman
981 | 2020-05-04 | MEDORE_CR18_JLT | Bitar response to Raft & Column str dwgs
982 | 2020-05-04 | MEDORE_CR18_JLT | Final column numbers
983 | 2020-05-04 | MEDORE_CR18_JLT | Slab strengthening Rejected
984 | 2020-05-04 | MEDORE_CR18_JLT | Bitar reply to Rejection
985 | 2020-05-04 | MEDORE_CR18_JLT | Structural clarification - 1st floor
986 | 2020-05-04 | MEDORE_CR18_JLT | Undertaking letter DM - BV
987 | 2020-05-04 | MEDORE_CR18_JLT | Response to B4 as letter
988 | 2020-05-04 | MEDORE_CR18_JLT | Bitar reply struc clarification
989 | 2020-05-05 | MEDORE_CR18_JLT | CCL updated license
990 | 2020-05-05 | MEDORE_CR18_JLT | Floor wise Qty breakdown needed
991 | 2020-05-05 | MEDORE_CR18_JLT | We are preparing
992 | 2020-05-05 | MEDORE_CR18_JLT | Water leakage photos - atef
993 | 2020-05-06 | MEDORE_CR18_JLT | Any concern
994 | 2020-05-06 | MEDORE_CR18_JLT | 8th to 19th floor letter from CR18
995 | 2020-05-06 | MEDORE_CR18_JLT | Already highlighted - Bitar
996 | 2020-05-06 | MEDORE_CR18_JLT | Reminder for program
997 | 2020-05-06 | MEDORE_CR18_JLT | Site observation # 1 cracks to afsal
998 | 2020-05-06 | MEDORE_CR18_JLT | IR for wet cracks
999 | 2020-05-06 | MEDORE_CR18_JLT | Invoice from conmix
1000 | 2020-05-06 | MEDORE_CR18_JLT | Strengthening BOQ to Arif
1001 | 2020-05-06 | MEDORE_CR18_JLT | Conmix invoice fwd mena
1002 | 2020-05-06 | MEDORE_CR18_JLT | Atef updated program
1003 | 2020-05-06 | MEDORE_CR18_JLT | 8th to 19th floor bitar response email
1004 | 2020-05-06 | MEDORE_CR18_JLT | Response to 8th to 19th floor comments letter
1005 | 2020-05-06 | MEDORE_CR18_JLT | Need Qty breakdown
1006 | 2020-05-06 | MEDORE_CR18_JLT | Fosroc injection materials
1007 | 2020-05-07 | MEDORE_CR18_JLT | Materials required
1008 | 2020-05-07 | MEDORE_CR18_JLT | Need A1 and A4 prints
1009 | 2020-05-07 | MEDORE_CR18_JLT | Need updated program
1010 | 2020-05-09 | MEDORE_CR18_JLT | Steel material submittal still not
1011 | 2020-05-09 | MEDORE_CR18_JLT | Steel cleaning Mockup Approval
1012 | 2020-05-10 | MEDORE_CR18_JLT | Updated program to Vijesh
1013 | 2020-05-10 | MEDORE_CR18_JLT | Reminder Sugin USW Steel mat submittal
1014 | 2020-05-10 | MEDORE_CR18_JLT | By tomorrow
1015 | 2020-05-10 | MEDORE_CR18_JLT | Breakdown BOQ
1016 | 2020-05-10 | MEDORE_CR18_JLT | Updated BoQ
1017 | 2020-05-10 | MEDORE_CR18_JLT | Breakdown BOQ to Atif
1018 | 2020-05-10 | MEDORE_CR18_JLT | Updated report required by CR18
1019 | 2020-05-11 | MEDORE_CR18_JLT | Revised Mat. Submittal USW
1020 | 2020-05-11 | MEDORE_CR18_JLT | Reply to Sugin for Hard copies
1021 | 2020-05-11 | MEDORE_CR18_JLT | By tomorrow
1022 | 2020-05-11 | MEDORE_CR18_JLT | L-20 to L-30 slabs from CR18
1023 | 2020-05-11 | MEDORE_CR18_JLT | Soft reminder Afsal for wet crack issues
1024 | 2020-05-11 | MEDORE_CR18_JLT | Reply by Nithin from CR18
1025 | 2020-05-12 | MEDORE_CR18_JLT | B3, B2, LB updated dwgs Fwd Sameh
1026 | 2020-05-12 | MEDORE_CR18_JLT | Kurt arrange drawings
1027 | 2020-05-12 | MEDORE_CR18_JLT | B3, B2 and LB
1028 | 2020-05-12 | MEDORE_CR18_JLT | Updated link
1029 | 2020-05-12 | MEDORE_CR18_JLT | B3, B2 and LB to Afsal
1030 | 2020-05-12 | MEDORE_CR18_JLT | Revise Qty sheet
1031 | 2020-05-12 | MEDORE_CR18_JLT | Letter format to Bitar
1032 | 2020-05-12 | MEDORE_CR18_JLT | Afsal to Bitar - Core wall related BV
1033 | 2020-05-12 | MEDORE_CR18_JLT | Will get back
1034 | 2020-05-13 | MEDORE_CR18_JLT | Resubmit model
1035 | 2020-05-13 | MEDORE_CR18_JLT | We don’t have models
1036 | 2020-05-13 | MEDORE_CR18_JLT | A3 resubmission
1037 | 2020-05-13 | MEDORE_CR18_JLT | Bitar reply BV comments
1038 | 2020-05-14 | MEDORE_CR18_JLT | Arrange B3, B2, LB submittal link
1039 | 2020-05-14 | MEDORE_CR18_JLT | Make USW steel CD
1040 | 2020-05-14 | MEDORE_CR18_JLT | Shuttering required
1041 | 2020-05-14 | MEDORE_CR18_JLT | 31st to 37th slabs
1042 | 2020-05-14 | MEDORE_CR18_JLT | Stengulf email for shuttering
1043 | 2020-05-14 | MEDORE_CR18_JLT | Height of panels
1044 | 2020-05-16 | MEDORE_CR18_JLT | 8th to 19th floor PT comments letter
1045 | 2020-05-16 | MEDORE_CR18_JLT | Site works report
1046 | 2020-05-17 | MEDORE_CR18_JLT | Beam cutting - GF & 1st floor
1047 | 2020-05-17 | MEDORE_CR18_JLT | Updated breakdown to CR18
1048 | 2020-05-17 | MEDORE_CR18_JLT | GF and 1st floor IFC response to Afsal
1049 | 2020-05-17 | MEDORE_CR18_JLT | UB to 7th floor reminder to Afsal
1050 | 2020-05-17 | MEDORE_CR18_JLT | Height reply to Dennis stengulf
1051 | 2020-05-17 | MEDORE_CR18_JLT | Back-propping revise
1052 | 2020-05-17 | MEDORE_CR18_JLT | Sandblasting photos
1053 | 2020-05-17 | MEDORE_CR18_JLT | Reply to reagan
1054 | 2020-05-17 | MEDORE_CR18_JLT | Updated draft calculation (omar)
1055 | 2020-05-17 | MEDORE_CR18_JLT | Already sent to Consultant
1056 | 2020-05-17 | MEDORE_CR18_JLT | Steel corrosion MS prints
1057 | 2020-05-17 | MEDORE_CR18_JLT | UB to 7th still with Consultant
1058 | 2020-05-17 | MEDORE_CR18_JLT | Make CD
1059 | 2020-05-19 | MEDORE_CR18_JLT | Hoist beam will be additional
1060 | 2020-05-19 | MEDORE_CR18_JLT | Site mock-up location
1061 | 2020-05-19 | MEDORE_CR18_JLT | CCL cutting subcon to visit
1062 | 2020-05-20 | MEDORE_CR18_JLT | Back-propping approved
1063 | 2020-05-20 | MEDORE_CR18_JLT | Steel cleaning why resubmit
1064 | 2020-05-20 | MEDORE_CR18_JLT | Afsal to atef for mockup
1065 | 2020-05-20 | MEDORE_CR18_JLT | Qtn for 2 beam cutting
1066 | 2020-05-20 | MEDORE_CR18_JLT | Atef confirmed afsal
1067 | 2020-05-20 | MEDORE_CR18_JLT | Consultant letter - DM related
1068 | 2020-05-20 | MEDORE_CR18_JLT | Stengulf shuttering Qtn
1069 | 2020-05-20 | MEDORE_CR18_JLT | Bitar letter reply as email
1070 | 2020-05-21 | MEDORE_CR18_JLT | Compliance updates - New corrosion MS
1071 | 2020-05-21 | MEDORE_CR18_JLT | Correction
1072 | 2020-05-21 | MEDORE_CR18_JLT | Pages for correction
1073 | 2020-05-26 | MEDORE_CR18_JLT | Invoice # 1 to atef for review
1074 | 2020-05-26 | MEDORE_CR18_JLT | Invoice # 1 to Mena
1075 | 2020-05-26 | MEDORE_CR18_JLT | Work progress
1076 | 2020-05-26 | MEDORE_CR18_JLT | Afsal for water removal
1077 | 2020-05-26 | MEDORE_CR18_JLT | Beam cutting photos
1078 | 2020-05-26 | MEDORE_CR18_JLT | Beam cutting sketch
1079 | 2020-05-27 | MEDORE_CR18_JLT | Mat. Submittal approval update USW
1080 | 2020-05-27 | MEDORE_CR18_JLT | Bitar reply beam cutting
1081 | 2020-05-27 | MEDORE_CR18_JLT | Bitar reply Afsal Etabs
1082 | 2020-05-27 | MEDORE_CR18_JLT | Mention VO (afsal to bitar)
1083 | 2020-05-27 | MEDORE_CR18_JLT | Bitar to Afsal - No option 1
1084 | 2020-05-27 | MEDORE_CR18_JLT | Safety violation letter from CR18
1085 | 2020-05-27 | MEDORE_CR18_JLT | Site report - Nageh - Photos
1086 | 2020-05-28 | MEDORE_CR18_JLT | Proforma invoice
1087 | 2020-05-28 | MEDORE_CR18_JLT | Afsal latest Etabs model
1088 | 2020-05-28 | MEDORE_CR18_JLT | Bitar queries
1089 | 2020-05-28 | MEDORE_CR18_JLT | Lets proceed as team
1090 | 2020-05-28 | MEDORE_CR18_JLT | Technical queries - Bitar
1091 | 2020-05-28 | MEDORE_CR18_JLT | Suleiman reply Afsal
1092 | 2020-05-28 | MEDORE_CR18_JLT | Afsal with Consultant reply
1093 | 2020-05-28 | MEDORE_CR18_JLT | Bitar disagree
1094 | 2020-05-28 | MEDORE_CR18_JLT | Proceed with checking
1095 | 2020-05-28 | MEDORE_CR18_JLT | Arrange LPO for Conmix
1096 | 2020-05-28 | MEDORE_CR18_JLT | UB to 7th floor letter
1097 | 2020-05-28 | MEDORE_CR18_JLT | Conmix LPO
1098 | 2020-05-28 | MEDORE_CR18_JLT | Corrosion approval
1099 | 2020-05-28 | MEDORE_CR18_JLT | VO # 1 bitar
1100 | 2020-05-28 | MEDORE_CR18_JLT | Reply to Sugin for Mat submittal USW
1101 | 2020-05-28 | MEDORE_CR18_JLT | LPO to Conmix Muru
1102 | 2020-05-28 | MEDORE_CR18_JLT | Scope only checking
1103 | 2020-05-28 | MEDORE_CR18_JLT | Updated
1104 | 2020-05-28 | MEDORE_CR18_JLT | Beam cutting drawings from CR18
1105 | 2020-05-28 | MEDORE_CR18_JLT | Proceed
1106 | 2020-05-28 | MEDORE_CR18_JLT | Corrosion approval CR18
1107 | 2020-05-28 | MEDORE_CR18_JLT | VO # 1 to CR18 - Etabs wall cutting
1108 | 2020-05-28 | MEDORE_CR18_JLT | Draft letter bitar
1109 | 2020-05-28 | MEDORE_CR18_JLT | Comments
1110 | 2020-05-28 | MEDORE_CR18_JLT | Site report - Corrosion protection photos
1111 | 2020-05-30 | MEDORE_CR18_JLT | Raft & Col str. Letter CR18
1112 | 2020-05-30 | MEDORE_CR18_JLT | 8th 9th 10th confirmation letter req
1113 | 2020-05-30 | MEDORE_CR18_JLT | Official letter for confirmation letter req
1114 | 2020-05-30 | MEDORE_CR18_JLT | Cutting works Qtn
1115 | 2020-05-30 | MEDORE_CR18_JLT | Site report - Corrosion protection photos
1116 | 2020-05-31 | MEDORE_CR18_JLT | Etabs model reply Afsal
1117 | 2020-05-31 | MEDORE_CR18_JLT | UB to 7th letter to CR18
1118 | 2020-05-31 | MEDORE_CR18_JLT | VO # 2 cutting of beams
1119 | 2020-05-31 | MEDORE_CR18_JLT | Warning letter response
1120 | 2020-05-31 | MEDORE_CR18_JLT | VO accepted 6000
1121 | 2020-05-31 | MEDORE_CR18_JLT | Drop panel estimation
1122 | 2020-05-31 | MEDORE_CR18_JLT | ETABS model afsal
1123 | 2020-05-31 | MEDORE_CR18_JLT | Draft undertaking USW
1124 | 2020-05-31 | MEDORE_CR18_JLT | Fwd Sameh
1125 | 2020-05-31 | MEDORE_CR18_JLT | Site report - Steel corrosion photos
1126 | 2020-06-01 | MEDORE_CR18_JLT | Email DBMT Steel DCL
1127 | 2020-06-01 | MEDORE_CR18_JLT | Email Technosteel Steel DCL
1128 | 2020-06-01 | MEDORE_CR18_JLT | Column capacity Level-08 to 11 casting
1129 | 2020-06-01 | MEDORE_CR18_JLT | DBMT Terrance reply
1130 | 2020-06-01 | MEDORE_CR18_JLT | Technosteel reply
1131 | 2020-06-01 | MEDORE_CR18_JLT | Updated undertaking to USW
1132 | 2020-06-01 | MEDORE_CR18_JLT | Will submit tomorrow
1133 | 2020-06-02 | MEDORE_CR18_JLT | Steel plate Consultant reply
1134 | 2020-06-02 | MEDORE_CR18_JLT | Consultant reply steel mat. submittal
1135 | 2020-06-02 | MEDORE_CR18_JLT | Conmix LPO (not req)
1136 | 2020-06-03 | MEDORE_CR18_JLT | IR for trial mix of concrete
1137 | 2020-06-04 | MEDORE_CR18_JLT | HSE compliance audit letter
1138 | 2020-06-04 | MEDORE_CR18_JLT | Afsal to Bitar - 3rd party comments
1139 | 2020-06-04 | MEDORE_CR18_JLT | Connect models (afsal)
1140 | 2020-06-04 | MEDORE_CR18_JLT | Omar will speak (bitar)
1141 | 2020-06-06 | MEDORE_CR18_JLT | When can we get (afsal)
1142 | 2020-06-06 | MEDORE_CR18_JLT | Tomorrow (bitar)
1143 | 2020-06-06 | MEDORE_CR18_JLT | No more changes (bitar)
1144 | 2020-06-06 | MEDORE_CR18_JLT | MOM of progress meeting
1145 | 2020-06-07 | MEDORE_CR18_JLT | USW reminder for mat submittal
1146 | 2020-06-07 | MEDORE_CR18_JLT | Walkway at UB RFI
1147 | 2020-06-07 | MEDORE_CR18_JLT | Afsal to Bitar
1148 | 2020-06-07 | MEDORE_CR18_JLT | Steel submittal response to CR18
1149 | 2020-06-07 | MEDORE_CR18_JLT | UB to 7th floor letter
1150 | 2020-06-07 | MEDORE_CR18_JLT | Nothing for columns
1151 | 2020-06-07 | MEDORE_CR18_JLT | Design MOM email
1152 | 2020-06-07 | MEDORE_CR18_JLT | Letter fwd
1153 | 2020-06-07 | MEDORE_CR18_JLT | PT slab meeting minutes reply
1154 | 2020-06-08 | MEDORE_CR18_JLT | SAFE model letter
1155 | 2020-06-08 | MEDORE_CR18_JLT | Proforma invoice
1156 | 2020-06-08 | MEDORE_CR18_JLT | Good
1157 | 2020-06-08 | MEDORE_CR18_JLT | ETABS model rev-03
1158 | 2020-06-08 | MEDORE_CR18_JLT | SAFE model letter to CR18
1159 | 2020-06-10 | MEDORE_CR18_JLT | MEDORE Strengthening Slabs
1160 | 2020-06-10 | MEDORE_CR18_JLT | CCL undertaking L8-19
1161 | 2020-06-10 | MEDORE_CR18_JLT | CCL undertaking L8-19
1162 | 2020-06-10 | MEDORE_CR18_JLT | Micro-concrete testing
1163 | 2020-06-10 | MEDORE_CR18_JLT | Murugesan reply
1164 | 2020-06-10 | MEDORE_CR18_JLT | Final Report Findings & Strengthening Method
1165 | 2020-06-11 | MEDORE_CR18_JLT | Costing proposal
1166 | 2020-06-11 | MEDORE_CR18_JLT | To roland
1167 | 2020-06-11 | MEDORE_CR18_JLT | bitar no comments
1168 | 2020-06-11 | MEDORE_CR18_JLT | Call me
1169 | 2020-06-11 | MEDORE_CR18_JLT | Murugesan reply for bonding
1170 | 2020-06-11 | MEDORE_CR18_JLT | Changes
1171 | 2020-06-11 | MEDORE_CR18_JLT | Report to roland
1172 | 2020-06-11 | MEDORE_CR18_JLT | Approved 3 slabs
1173 | 2020-06-11 | MEDORE_CR18_JLT | Make CD
1174 | 2020-06-11 | MEDORE_CR18_JLT | Cost for Ext PT and CFRP (Atef)
1175 | 2020-06-11 | MEDORE_CR18_JLT | Riyaz fwd email
1176 | 2020-06-13 | MEDORE_CR18_JLT | Arif reply for new costing Qtn
1177 | 2020-06-13 | MEDORE_CR18_JLT | Riyaz about breakdown
1178 | 2020-06-13 | MEDORE_CR18_JLT | Bitar reply
1179 | 2020-06-13 | MEDORE_CR18_JLT | Cube testing
1180 | 2020-06-13 | MEDORE_CR18_JLT | MOM # 24
1181 | 2020-06-13 | MEDORE_CR18_JLT | Water leakage letter
1182 | 2020-06-13 | MEDORE_CR18_JLT | USW request about advance
1183 | 2020-06-14 | MEDORE_CR18_JLT | Reply to Riyaz
1184 | 2020-06-14 | MEDORE_CR18_JLT | Reply to USW safeer
1185 | 2020-06-14 | MEDORE_CR18_JLT | Confirm specs
1186 | 2020-06-14 | MEDORE_CR18_JLT | Were forwarded by client
1187 | 2020-06-14 | MEDORE_CR18_JLT | Sabeer to atef for cube testing
1188 | 2020-06-14 | MEDORE_CR18_JLT | IRs for crack injection to Mena
1189 | 2020-06-14 | MEDORE_CR18_JLT | Mena to Kaliraj
1190 | 2020-06-14 | MEDORE_CR18_JLT | Atef reply Sabeer
1191 | 2020-06-14 | MEDORE_CR18_JLT | Sabeer reply atef about testing
1192 | 2020-06-14 | MEDORE_CR18_JLT | Sabeer rates for testing
1193 | 2020-06-14 | MEDORE_CR18_JLT | Approved by Sameh
1194 | 2020-06-14 | MEDORE_CR18_JLT | Leakage arrest delay letter
1195 | 2020-06-15 | MEDORE_CR18_JLT | Pull-off test response Sabeer
1196 | 2020-06-15 | MEDORE_CR18_JLT | Specs reference by Sabeer
1197 | 2020-06-15 | MEDORE_CR18_JLT | Basement-3 crack photos
1198 | 2020-06-15 | MEDORE_CR18_JLT | Basement-2 crack photos
1199 | 2020-06-15 | MEDORE_CR18_JLT | LB crack photos
1200 | 2020-06-15 | MEDORE_CR18_JLT | Cracks layout
1201 | 2020-06-15 | MEDORE_CR18_JLT | Mail to ACES for MS & Qtn
1202 | 2020-06-15 | MEDORE_CR18_JLT | Email to conmix for bonding letter
1203 | 2020-06-15 | MEDORE_CR18_JLT | BIM query 39th floor
1204 | 2020-06-15 | MEDORE_CR18_JLT | Ramp section & details
1205 | 2020-06-15 | MEDORE_CR18_JLT | Crack layout & site photos
1206 | 2020-06-15 | MEDORE_CR18_JLT | Conmix pull-off letter
1207 | 2020-06-16 | MEDORE_CR18_JLT | DM approved PT drawings
1208 | 2020-06-16 | MEDORE_CR18_JLT | Congrats
1209 | 2020-06-16 | MEDORE_CR18_JLT | Storage space email to Kaliraj
1210 | 2020-06-16 | MEDORE_CR18_JLT | Delay in Engineering Excel
1211 | 2020-06-16 | MEDORE_CR18_JLT | Clearance letter req (Riyaz)
1212 | 2020-06-16 | MEDORE_CR18_JLT | B3, B2, LB approval from Consultant
1213 | 2020-06-16 | MEDORE_CR18_JLT | Kaliraj reply to crack leakage issues
1214 | 2020-06-17 | MEDORE_CR18_JLT | Tendon report required Level-07
1215 | 2020-06-17 | MEDORE_CR18_JLT | Reply to Variation order # 3
1216 | 2020-06-17 | MEDORE_CR18_JLT | Design too (Bitar reply)
1217 | 2020-06-17 | MEDORE_CR18_JLT | Make CD
1218 | 2020-06-17 | MEDORE_CR18_JLT | Clearance draft letter
1219 | 2020-06-17 | MEDORE_CR18_JLT | Later
1220 | 2020-06-17 | MEDORE_CR18_JLT | Payment terms change letter to Fosroc
1221 | 2020-06-17 | MEDORE_CR18_JLT | Fosroc response
1222 | 2020-06-17 | MEDORE_CR18_JLT | Scanning report for Level-07 required
1223 | 2020-06-17 | MEDORE_CR18_JLT | ETABS
1224 | 2020-06-17 | MEDORE_CR18_JLT | ReCon MC5mm cube test result
1225 | 2020-06-17 | MEDORE_CR18_JLT | Results forwarded to Conmix
1226 | 2020-06-18 | MEDORE_CR18_JLT | Safeer email USW
1227 | 2020-06-18 | MEDORE_CR18_JLT | Resend letter
1228 | 2020-06-18 | MEDORE_CR18_JLT | Revised clearance Level-08 to 10
1229 | 2020-06-18 | MEDORE_CR18_JLT | Noted
1230 | 2020-06-18 | MEDORE_CR18_JLT | Mapei profile
1231 | 2020-06-18 | MEDORE_CR18_JLT | VAT to jamal
1232 | 2020-06-18 | MEDORE_CR18_JLT | Column steel jacketing material approval
1233 | 2020-06-20 | MEDORE_CR18_JLT | Scanning reminder
1234 | 2020-06-20 | MEDORE_CR18_JLT | WIR column chipping
1235 | 2020-06-20 | MEDORE_CR18_JLT | Column steel jacketing material approval
1236 | 2020-06-20 | MEDORE_CR18_JLT | MSRA and PQ copies required
1237 | 2020-06-20 | MEDORE_CR18_JLT | APG response to clearance letter
1238 | 2020-06-21 | MEDORE_CR18_JLT | Steel plate testing requirement
1239 | 2020-06-21 | MEDORE_CR18_JLT | Fwd to USW
1240 | 2020-06-21 | MEDORE_CR18_JLT | Can be done after procurement
1241 | 2020-06-21 | MEDORE_CR18_JLT | Level-07 scanning report
1242 | 2020-06-21 | MEDORE_CR18_JLT | Raft thickening concrete details required
1243 | 2020-06-22 | MEDORE_CR18_JLT | Raft mix design
1244 | 2020-06-22 | MEDORE_CR18_JLT | fwd to CCL
1245 | 2020-06-22 | MEDORE_CR18_JLT | Lootah concrete price
1246 | 2020-06-23 | MEDORE_CR18_JLT | Reminder ACES
1247 | 2020-06-23 | MEDORE_CR18_JLT | Fosroc credit letter
1248 | 2020-06-23 | MEDORE_CR18_JLT | Pull-off test methodology grout
1249 | 2020-06-23 | MEDORE_CR18_JLT | Pricing for pull-off ACES
1250 | 2020-06-23 | MEDORE_CR18_JLT | Work progress - various projects
1251 | 2020-06-23 | MEDORE_CR18_JLT | Need LPO
1252 | 2020-06-23 | MEDORE_CR18_JLT | Make LPO Fosroc